## Slide 1
EXECUTIVE DELIVERY OVERVIEW
Delivery plan & project controls
A compact, evidence-based SDLC plan for closing prototype gaps without presenting planned work as delivered.
As of 2026-10-14 | Current implementation and proposed next steps clearly separated
BRONZE
Raw trades and daily prices
SILVER
Typed, validated, rejected
GOLD
Positions, valuation, P&L

## Slide 2
Project overview | evidence before roadmap
01 | DELIVERY BASELINE
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
02
Problem
Reconcile synthetic equity trades and daily prices into positions, valuation, P&L, and visible operational exceptions.
Already implemented
Six-task Databricks Workflow; 10 Delta tables; trade/price validation; positions; simplified daily P&L; audit/rejects; notebooks/SQL.
Next delivery
Approved source contracts, trade snapshot semantics, CI/deploy controls, complete rerun evidence, dashboard MVP, and runbook/alerts.
Dated verification: 2026-10-11 run completed all six tasks; 5,990 position rows and 835 P&L rows reconciled with zero reported calculation mismatches.
Caveat: the same-parameter second run was queued and has no recorded result. The configured schedule is paused and this is a proof of concept, not a production service.

## Slide 3
SDLC approach | decisions flow into evidence
02 | REQUIREMENTS AND TRACEABILITY
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
03
Discover
Stakeholders Source contracts Scope and RAID
Specify
BR / FR / NFR Data dictionary Calculation policy
Design
Architecture DAG / table grains Security boundary
Build & verify
Stories / subtasks Tests / reconciliation PR + Bundle
Release
UAT / readiness Runbook / monitor Controlled schedule
Traceability is maintained from BR-001..008 → FR-001..013 → TMP story IDs → TC test cases → acceptance evidence. Decisions and gaps stay explicit in the workbook RAID and decision log.
Definition of Ready: owner, input contract, dependencies, AC, estimate, and test evidence agreed. Definition of Done: reviewed code/config, tests passed (skips disclosed), reconciled data, deploy evidence, docs, and operational owner.

## Slide 4
Jira structure | implementation status is separate
03 | BACKLOG
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
04
13 epics
SDLC stages and engineering capabilities
24 stories
Requirements, design, build, test, operations
48 subtasks
Specific engineering outputs under stories
Planning IDs are temporary and consistent across workbook, decks, and Jira CSV.
IMPLEMENTED
Done in current repo/runtime evidence
PARTIAL
Code exists; evidence/control gap remains
PLANNED
Backlog only; not delivered
CSV import mapping: Planning Key should map to a custom field; Issue Type, Summary, Description, Priority, Story Points, and Status to Jira fields; Epic Name/Epic Link/Parent ID to hierarchy fields. Import epics first and resolve temporary Epic Link values to generated Jira keys if required by the Jira edition.

## Slide 5
Dependency-driven execution sequence
04 | CRITICAL PATH
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
05
Source + scope TMP-001/002/006/007
Data / security TMP-003/005/008
Controls + history TMP-010/012/016
Reporting + UAT TMP-020/022
Handover TMP-024
Parallel workstream A | trades
Trade contract → Bronze snapshot → Silver versioning → position/P&L correction reconciliation
Parallel workstream B | prices
Provider decision → Bronze prices → Silver completeness → position valuation / P&L baseline
Critical path: business/source decisions → supported integration and rerun evidence → safe deployment controls → dashboard/UAT → handover. Dashboard build can start only after reporting grain, access, and price/trade contracts are agreed.

## Slide 6
Proposed two-week sprint plan
05 | EIGHT-WEEK BASELINE
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
06
Sprint 1 | Weeks 1-2
Lock project scope, requirement acceptance, measurable NFRs, and target access design. TMP-001, TMP-002, TMP-003, TMP-005 | 10 SP
Sprint 2 | Weeks 3-4
Resolve market-data decisions, dictionary, price exception handling, and runtime test strategy. TMP-007, TMP-008, TMP-014, TMP-016 | 10 SP
Sprint 3 | Weeks 5-6
Improve deployment controls and resolve trade snapshot history/correction semantics. TMP-010, TMP-012 | 10 SP
Sprint 4 | Weeks 7-8
Deliver reporting MVP, reconciliation/UAT evidence, and operations handover. TMP-020, TMP-022, TMP-024 | 10 SP
40 SP / 8 weeks = assumed 10 SP per sprint. No reserve; relative weeks, not approved delivery dates. Use one contingency sprint if source/access decisions slip.

## Slide 7
Principal project risks and controls
06 | RAID
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
07
Provider approval
High / High
Yahoo Finance is current prototype only; data rights and SLA unconfirmed.
Select approved source; keep production blocked until sign-off.
Snapshot semantics
Medium / High
Trade IDs absent from a newer file are not deleted from Silver.
Agree cancellation/deletion rule; test two-snapshot reconciliation.
Capacity and decisions
Medium / High
40 SP baseline has no reserve; part-time owners and runtime access gate work.
Book owners at kickoff; defer polish or add one sprint.
Operational readiness
High / High
Dev only, paused schedule, no automated alerts or production identity.
Readiness gate; least privilege, alert test, runbook and sign-off.

## Slide 8
Delivery gates and immediate next steps
07 | DECISIONS
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
08
1 | Confirm owners
Trade source and correction semantics Market-data rights / provider Product/reporting audience Platform identity and test runtime
2 | Close evidence gaps
Run same-input Databricks job twice Execute Spark/Delta integration tests Capture duration and failure recovery Approve NFR / retention / recovery targets
3 | Gate release
Complete dashboard UAT Review access and alerts Handover runbook and ownership Keep schedule paused until readiness sign-off
Milestones: W2 scope/requirements | W4 source/model | W6 controls/history | W8 UAT/handover.
Interview framing: a real prototype already demonstrates the Medallion flow and financial calculation checks. The plan is about controlled completion: approved sources, explicit business semantics, reproducible tests/deployments, user acceptance, and operations. Do not claim production delivery, a dashboard, or a successful rerun that is not evidenced.