## Slide 1
Project overview | problem, objectives and scope
01 | DELIVERY BASELINE
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
01
Business problem
Trade snapshots and daily equity prices need controlled validation, position aggregation, valuation, P&L and exception visibility.
Objective
Databricks trading data processing and daily P&L proof of concept
Technology and scope
Databricks; PySpark / SQL; Delta Lake; Unity Catalog; Workflows; Asset Bundle; synthetic trades; prototype prices.
Current implementation is a technical proof of concept. The brief says Azure Databricks, while workspace evidence indicates AWS; target cloud needs confirmation. No production banking deployment or approval is claimed.
Boundaries: USD equities, ten configured symbols, simplified daily P&L; FX, derivatives, fees, dividends and corporate actions are excluded.
Notes: TPM perspective: establish the actual baseline first, then state the proposed work. Quote dated run evidence and its limitations accurately.

## Slide 2
Business value and measurable success criteria
02 | BUSINESS VALUE
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
03
Trade completeness
Exact 14-column input contract; invalid file cannot replace the prior Bronze snapshot.
Position accuracy
Daily signed quantities reconcile by date, book, counterparty and instrument.
P&L integrity
Daily P&L reconciles using approved inputs; missing required marks remain NULL with breaks.
Operational control
Every task attempt is auditable; identical-input rerun preserves business outputs (proposed acceptance; rerun not verified).
Verified evidence: 2026-10-11 Databricks run had six successful tasks; 5,990 positions and 835 P&L rows had zero reported independent SQL mismatches. This is one run, not a service-level commitment.
Notes: TPM perspective: connect measurable outcomes to acceptance evidence. Targets marked proposed remain discussion points until owners approve them.

## Slide 3
Stakeholder landscape and decision ownership
03 | STAKEHOLDERS
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
04
Business and control
Sponsor: scope/capacity/go-no-go BA / Product Owner: requirements and acceptance Product Control: calculation and reconciliation approval Trading Operations: trade source and operating semantics
Technology delivery
TPM: integrated plan, RAID, dependencies, governance Solution Architect: architecture and decisions Data Engineering: implementation and technical evidence QA: test evidence and defect visibility
Control / operations
Information Security: access and policy review Production Support: monitoring, recovery and handover Market Data Owner: provider rights and service contract Named participants and approvals: NOT VERIFIED
RACI is proposed for planning; role ownership must be confirmed at mobilisation.
Notes: TPM perspective: clarify decision rights and escalation routes. Roles shown are proposed stakeholder functions, not named participants or completed interviews.

## Slide 4
Solution architecture | preserve the working core
04 | ARCHITECTURE
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
05
Inputs
Synthetic trade CSV Yahoo Finance prototype
Bronze
Raw Delta + lineage
Silver
Typed data + rejects
Gold positions
Daily inventory + value
Gold P&L
Daily result + breaks + audit
Consumers
Report notebook + SQL Dashboard: PLANNED
Orchestration: two independent source branches → Silver join at build_positions → calculate_daily_pnl. Databricks Workflow, Unity Catalog cibc and Asset Bundle dev target are implemented; production targets and security controls remain gated.
Notes: TPM perspective: connect the technical evidence to an accountable decision, dependency, acceptance gate, or risk. Label assumptions and unverified results explicitly.

## Slide 5
Requirements traceability | from outcome to evidence
04 | REQUIREMENTS
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
06
BR-005
Calculate daily position valuation and daily P&L.
FR-008
Calculate daily equity P&L separating opening-position price movement from trade-day economics.
TMP-018
Calculate daily cash-equity mark-to-market P&L
TC-006
Opening-position price move + trade-day cash-flow term; missing baseline/current close
Acceptance
Independent test examples match; activity quantity changes do not create false opening-position P&L.
Evidence
tests/test_daily_pnl.py; documented BOOK_TECH/AAPL hand check
The workbook traceability matrix covers all BR → FR → story → test/evidence mappings; IDs are shared with the CSV.
Notes: TPM perspective: show the control chain from business outcome to acceptance evidence. Traceability makes scope changes assessable rather than informal.

## Slide 6
Delivery strategy | capability-based backlog
05 | DELIVERY STRATEGY
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
07
7 epics
Outcome-oriented capabilities
24 stories
82 estimated points across current + proposed work
48 subtasks
Specific evidence under each story
Delivery approach: clarify scope and acceptance → design/data contracts → build in parallel workstreams → verify with tests and reconciliation → release only after readiness gate.
8-week baseline: 38 SP planned against 40 assumed capacity (10 SP/sprint); 2 SP aggregate headroom, not a guaranteed reserve. Optional Sprint 5: 10 SP for data approval, price exception operations and dashboard.
Current implementation stories retain evidence status. Their point values are reference estimates, not remaining-work effort or actual velocity.
Notes: TPM perspective: plan around capability outcomes and dependencies. Current implementation items are evidence, not new delivery points.

## Slide 7
Integrated delivery roadmap | relative weeks
06 | ROADMAP
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
08
Weeks 1-2 | 9 SP
M-01
TMP-001; TMP-002; TMP-003; TMP-006
Baseline scope, requirements, NFRs, and trade source semantics; identify decision owners.
Weeks 3-4 | 9 SP
M-02
TMP-005; TMP-007; TMP-023
Close target access design, market-data decision, and controlled dev operating procedure.
Weeks 5-6 | 10 SP
M-03
TMP-010; TMP-012
Establish reviewed CI/deployment controls and resolve trade snapshot correction behavior.
Weeks 7-8 | 10 SP
M-04
TMP-016; TMP-021; TMP-022; TMP-024
Close test failures, supported-runtime rerun/reconciliation, and operational handover.
Weeks 9-10 (follow-on; not in 8-week baseline) | 10 SP | optional
M-05
TMP-008; TMP-014; TMP-020
Complete follow-on data approval, missing-price operations, dictionary approval, and dashboard MVP if authorized.
Baseline: 38/40 SP; 2 SP headroom. Optional Sprint 5 is follow-on, not contingency capacity committed to this baseline. Relative weeks only.
Notes: TPM perspective: use relative weeks and capacity assumptions only. Reforecast when source, access, or stakeholder decisions move; optional work is not hidden in the baseline.

## Slide 8
Dependency drivers and delivery constraints
07 | DEPENDENCY DRIVERS
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
09
Trade workstream
Source contract → Bronze snapshot → Silver version/correction rules → positions → P&L reconciliation
Price workstream
Provider decision → Bronze prices → Silver completeness → position valuation / P&L baseline
Join and release dependencies
Both Silver outputs → positions → P&L → supported-runtime tests / reconciliation → UAT → handover
Dependency-led candidate sequence only; not a CPM-calculated critical path. Story-point estimates and sprint timeboxes do not provide activity durations, resource leveling, or float. External constraints: market-data rights, source-owner decisions, Spark/Delta test access, Security review, Product Control sign-off, and support availability.
Notes: TPM perspective: distinguish a dependency-led sequence from a CPM critical path. We lack activity durations, resource leveling, and float to calculate the latter.

## Slide 9
Risk and governance | proportionate control
08 | RISK AND GOVERNANCE
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
10
R-01 | High / High
Yahoo Finance is not established as an approved or licensed institutional market-data source.
R-02 | Medium / High
Full-snapshot trade Bronze can leave stale Silver trades when trade IDs disappear from later files.
R-03 | Medium / High
Full-history recomputation and free-form instrument/book data may not scale or satisfy control expectations.
R-04 | Medium / High
Eight-week plan has no capacity reserve and depends on part-time approvers and test runtime access.
Cadence
Daily engineering stand-up; weekly workstream + RAID; design/security reviews at gates; biweekly steering; milestone and release-readiness approvals.
Escalation
Trigger/owner/date in RAID; unresolved delivery blocker → TPM; business/scope trade-off → Sponsor; policy/security/data rights → accountable control owner.
Notes: TPM perspective: review triggers and owners weekly; escalate before the milestone is missed. Governance is deliberately proportionate to a small team.

## Slide 10
Testing and release readiness
09 | TEST AND RELEASE
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
11
Test evidence
Unit and schema tests Data-quality/reject tests Position and P&L reconciliation Same-input idempotency + failure recovery UAT and deployment smoke test
Known status
2026-10-11: six tasks succeeded; 5,990 positions and 835 P&L rows had zero reported mismatches 3 focused tests fail on removed DDL file references Same-input second Job run: NOT VERIFIED
No-go until
Supported Spark/Delta tests pass or disposition is approved Product Control accepts results Least privilege, alerts, recovery and support proven Source rights/retention/release owner approved
No CI workflow, production Bundle target, automated alerting, or schedule activation is evidenced in this repository.
Notes: TPM perspective: require reproducible evidence, business reconciliation, operational acceptance, and an explicit no-go path. Skips are not passes.

## Slide 11
Project status | what is and is not demonstrated
10 | STATUS
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
12
IMPLEMENTED STORIES
TMP-004 Document and validate existing solution architecture; TMP-009 Maintain reproducible Databricks Asset Bundle development deployment; TMP-011 Ingest synthetic trade snapshot into Bronze; TMP-013 Ingest and retain daily market-price history
PARTIALLY IMPLEMENTED
TMP-001 PARTIALLY IMPLEMENTED; TMP-006 PARTIALLY IMPLEMENTED; TMP-021 PARTIALLY IMPLEMENTED; TMP-022 PARTIALLY IMPLEMENTED; TMP-023 PARTIALLY IMPLEMENTED
PLANNED / BLOCKED / NOT VERIFIED
TMP-002 PLANNED; TMP-003 PLANNED; TMP-005 PLANNED; TMP-007 PLANNED; TMP-008 NOT VERIFIED
Overall status: AMBER for a demonstrated proof of concept; NOT VERIFIED for the proposed schedule, named resources, and enterprise readiness. Quality has known focused test failures.
Evidence baseline: repository and docs/test_results.md dated 2026-10-11; this plan is dated 2026-10-14.
Master backlog status example: TMP-016: PLANNED; TMP-018: IMPLEMENTED; TMP-022: PARTIALLY IMPLEMENTED
Notes: TPM perspective: report variance and uncertainty without spin. State known failures, unverified results, and the decision or owner needed to recover.

## Slide 12
Outcomes and next steps
11 | NEXT STEPS
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
13
Demonstrated
End-to-end Medallion path, auditable tasks, reject handling, position/P&L calculations, and independent SQL reconciliation for one documented run.
Leadership lessons
Make source ownership explicit; protect financial acceptance; plan dependencies before sprint commitments; surface test gaps early; separate prototype evidence from production claims.
Immediate decisions
Name decision owners; approve trade/price contracts; provision test runtime; close stale tests; confirm methodology; retain optional scope until capacity and audience are approved.
Production-readiness roadmap: source and rights → access/security → CI and repeatable deployment → test/reconciliation and UAT → monitoring/recovery and support → explicit release approval.
Keep the scheduled Job paused unless a separate readiness review approves activation.
Notes: TPM perspective: close the highest-risk decisions first, preserve the paused schedule, and make any added scope pass change control.

## Slide 13
Integrated Project Delivery Plan — Timeline & Dependencies
12 | INTEGRATED GANTT
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
14
KEY DELIVERY DEPENDENCIES — ILLUSTRATIVE BASELINE
Relative weeks; no kickoff date supplied
ID
WORKSTREAM / TASK
WINDOW
PREDECESSORS
SP
EVIDENCE
WEEK 1
WEEK 2
WEEK 3
WEEK 4
WEEK 5
WEEK 6
WEEK 7
WEEK 8
WS-01
Requirements and scope
2w*
-
7
PARTIAL
7 SP
WS-02
Trade source contract
2w*
-
2
PARTIAL
2 SP
WS-03
Security and environment design
2w*
W01/TMP-004
3
PLANNED
3 SP
WS-04
Market-data provider decision
2w*
W01
3
PLANNED
3 SP
WS-05
Workflow and schedule gate
2w*
TMP-009
3
PARTIAL
3 SP
WS-06
CI/CD promotion controls
2w*
W03/TMP-009
5
PLANNED
5 SP
WS-07
Trade correction and history
2w*
W02/TMP-011
5
PLANNED
5 SP
WS-08
Spark/Delta rerun validation
2w*
TMP-015
2
PLANNED
2 SP
WS-09
Test maintenance and QA
2w*
-
3
PARTIAL
3 SP
WS-10
Reconciliation and UAT
2w*
W08/TMP-018
2
PARTIAL
2 SP
WS-11
Operations handover
2w*
W01/W05/W10/TMP-019
3
PLANNED
3 SP
M-01
M-02
M-03
M-04
Implemented evidence (current, undated)
Partially implemented evidence
Planned sprint window
Milestone
Zero-float CPM critical path: none calculated
* Bars show two-week sprint allocation windows, not task durations. M-05 and the blocked dashboard are optional Week 9-10 follow-on; not on this 8-week axis.
Notes: TPM perspective: explain the bars as proposed sprint allocation windows, not task durations. The schedule uses relative weeks only; status colors distinguish evidence from planned schedule. Point out that no kickoff date or activity-level duration was supplied.

## Slide 14
Detailed Dependencies & Critical-Path Readiness
13 | DEPENDENCY DETAIL
TRADING PLATFORM | EVIDENCE BASELINE 2026-10-14 | PROPOSED DELIVERY PLAN
15
KEY DELIVERY DEPENDENCIES — ILLUSTRATIVE BASELINE
CPM dates and float are not calculated
WS-01 Requirements and scope
TMP-001; TMP-002; TMP-003
WS-03 Security and environment design
TMP-005
WS-06 CI/CD promotion controls
TMP-010
WS-02 Trade source contract
TMP-006
WS-07 Trade correction and history
TMP-012
Current Silver
TMP-015
WS-08 Spark/Delta rerun validation
TMP-016
WS-10 Reconciliation and UAT
TMP-022
WS-11 Operations handover
TMP-024
CPM status: NOT CALCULATED
Earliest start / finish: NOT AVAILABLE Latest start / finish: NOT AVAILABLE Total float: NOT AVAILABLE The repository has story points and sprint windows, not activity-level elapsed durations, a kickoff calendar, resource leveling, or approved lag/constraint data. No activity is outlined as critical.
Milestone impact
M-01 W2: requirements / trade contract M-02 W4: source / access decisions M-03 W6: controls / trade history M-04 W8: test, reconciliation and handover
Detailed predecessor register (FS = finish-to-start; current prerequisites are undated)
PREDECESSOR STORY IDs
SUCCESSOR
MILESTONE IMPACT
TMP-001; TMP-002
TMP-001; TMP-002; TMP-003
M-01 End Week 2 — Scope, requirements and trade contract baseline
TMP-002; TMP-003; current TMP-004
TMP-005
M-02 End Week 4 — Source and access design gate
TMP-002
TMP-007
M-02 End Week 4 — Source and access design gate
current TMP-009
TMP-023
M-02 End Week 4 — Source and access design gate
TMP-005; current TMP-009
TMP-010
M-03 End Week 6 — Engineering controls and trade-history gate
TMP-006; current TMP-011
TMP-012
M-03 End Week 6 — Engineering controls and trade-history gate
current TMP-015
TMP-016
M-04 End Week 8 — Prototype acceptance and handover
TMP-016; current TMP-018
TMP-022
M-04 End Week 8 — Prototype acceptance and handover
TMP-003; current TMP-019; TMP-022; TMP-023
TMP-024
M-04 End Week 8 — Prototype acceptance and handover
CPM inputs required: task durations, calendar start, complete lag-aware dependencies, and resource constraints. Optional Sprint 5 predecessors remain in the workbook/Jira register.
Notes: TPM perspective: walk the exact story-level finish-to-start relationships, including current but undated prerequisites. Explicitly state that CPM dates and float are not calculated because points and sprint windows do not provide activity durations or resource leveling.