## Executive Dashboard
TRADING PLATFORM ¦ EXECUTIVE PROJECT DASHBOARD
Evidence baseline | 2026-10-14; repository plus dated run evidence 2026-10-11
Purpose | Databricks trading data processing and daily P&L proof of concept
Area | RAG | Current position | Evidence / caveat | Decision owner | Next action
Overall project status | AMBER | Working technical proof of concept demonstrated; not a production banking implementation. | Six-task dev Job and 2026-10-11 run evidence; production controls and source approval remain open. | Role TBD | See decisions and RAID
Scope status | AMBER | USD cash-equity prototype is implemented; enterprise source, lifecycle, FX and accounting scope are not baselined. | README assumptions and source contracts. | Role TBD | See decisions and RAID
Schedule status | NOT VERIFIED | Proposed relative 8-week plan only; no kickoff date or actual sprint progress is evidenced. | No project execution schedule/actual dates in repository. | Role TBD | See decisions and RAID
Quality status | RED | Focused run found 3 stale DDL-path test failures; full-suite result and same-input Databricks rerun are not verified. | tests reference removed *_constraints.sql; docs/test_results.md second run queued. | Role TBD | See decisions and RAID
Resource status | NOT VERIFIED | Role capacities are planning assumptions; no named assignments or availability commitments are evidenced. | Proposed capacity plan only. | Role TBD | See decisions and RAID
Planning metric | Value | Meaning
Business requirements |  | Eight business outcomes
Functional requirements |  | Thirteen functional behaviors
Jira epics / stories / subtasks |  | Temporary planning IDs
Total estimated backlog points |  | Includes already implemented/reference scope; not remaining effort
8-week baseline points / capacity |  | 38 SP planned / 40 assumed; 2 SP headroom
Optional follow-on points |  | Sprint 5 Weeks 9-10; not in baseline
DDL dictionary columns |  | All 10 physical tables
Completed deliverables (verified prototype) | Six-task dev workflow; 10 Delta tables; synthetic 14-column trade CSV; Yahoo Finance adapter; Silver validation/rejects; positions and simplified daily P&L; audit/breaks; two notebooks and SQL.
Upcoming milestone | Target | Exit evidence | Accountable role | Dependencies | Approval gate
Scope, requirements and trade contract baseline | End Week 2 | Approved BR/FR/NFR decisions; trade source/version/correction semantics; named decision owners | Technical Project Manager / Product Owner | TMP-001; TMP-002; TMP-003; TMP-006 | Product Owner and Trade Data Owner; role names proposed, identities TBD
Source and access design gate | End Week 4 | Market-data source decision; target identity/access design; dev workflow gate | Solution Architect / Market Data Owner | TMP-005; TMP-007; TMP-023 | Platform/Security and Market Data Owner; no production access approval assumed
Engineering controls and trade-history gate | End Week 6 | CI evidence; trade correction/disappearance test; deployment control review | Lead Data Engineer / Technical Project Manager | TMP-010; TMP-012 | Engineering owner and Product Control review of affected trade semantics
Prototype acceptance and handover | End Week 8 | Supported-runtime tests; same-input rerun; reconciliation/UAT; runbook and support walkthrough | Product Control / Production Support | TMP-016; TMP-021; TMP-022; TMP-024 | Product Control, QA, Production Support, and Sponsor go/no-go for prototype exit
Optional dashboard and data sign-off | End Week 10 (optional follow-on) | Approved reporting/data decisions; dashboard reconciliation and role access | Product Owner / Product Control | TMP-008; TMP-014; TMP-020 | Product Owner, Product Control, and access owner
Top risks | Owner | Trigger | Mitigation | Escalation | Status
Yahoo Finance is not established as an approved or licensed institutional market-data source. | Market Data Owner | No approved provider/rights or completeness owner by source gate. | Obtain provider/data-rights decision in Sprint 2; keep production scope blocked until approved source is selected. | Market Data Owner → Sponsor; Security/Legal/Data Governance as applicable. | Open
Full-snapshot trade Bronze can leave stale Silver trades when trade IDs disappear from later files. | Trade Data Owner | A two-snapshot comparison leaves a trade in Silver after authoritative removal/correction. | Agree cancellation/deletion semantics and implement two-snapshot reconciliation test before relying on external trade feed. | Trading Operations and Product Control → Sponsor if semantics affect positions/P&L. | Open
Full-history recomputation and free-form instrument/book data may not scale or satisfy control expectations. | Lead Data Engineer | Representative-volume benchmark exceeds proposed runtime/cost or reference mapping is inconsistent. | Benchmark representative scale; establish reference ownership and incremental strategy from evidence. | Lead Engineer / Architect → TPM → Sponsor for scope/capacity decision. | Open
Eight-week plan has no capacity reserve and depends on part-time approvers and test runtime access. | Project Manager | Decision/access delay consumes the 2-point baseline headroom or threatens a gate. | Reserve decision owners at Sprint start; defer dashboard polish or extend by one sprint if critical access/decisions slip. | TPM → Sponsor; defer optional dashboard/follow-on or approve added capacity. | Open
Key dependencies | Source owners, market-data rights, supported Spark/Delta test runtime, access/security reviewer, Product Control acceptance, support owner.
Decisions required
Approve trade-source owner, delivery contract, completeness/correction/cancellation semantics.
Select and approve market-data provider, rights, close definition, SLA and exception owner.
Confirm calculation methodology and tolerance with Product Control; prototype formula is simplified USD cash equity.
Confirm named stakeholders, project capacity, and supported Spark/Delta test environment.
Approve environment identity, least-privilege access, retention, RTO/RPO, support model and release gate before non-dev use.
Confirm dashboard audience/tool; dashboard is blocked pending reporting and access decisions.

## Business Req
BR ID | Requirement | Business justification | Priority | Acceptance criteria | Dependencies | Implementation status | Functional requirements
BR-001 | Ingest trade transactions from an agreed source. | Provide complete, traceable trade activity for positions and P&L. | Must | A valid input snapshot is recorded in Bronze with source and run lineage; invalid file structure fails before replacing the prior snapshot. | Trade source contract; Unity Catalog Volume | IMPLEMENTED | FR-001; FR-003; FR-004; FR-005; FR-013
BR-002 | Ingest daily market prices for supported instruments. | Provide valuation marks and P&L inputs. | Must | Requested daily prices are recorded with source/date/currency lineage; missing expected sessions are visible and block incomplete Silver publication. | Provider availability and ticker universe | IMPLEMENTED | FR-002; FR-003; FR-005; FR-013
BR-003 | Maintain accurate trade records, including corrections and duplicates. | Prevent stale or ambiguous executions from contaminating financial results. | Must | One latest valid version per trade_id is used; invalid/ambiguous latest versions are excluded and explained; source-history limitations are disclosed. | Trade version contract; immutable source history decision | PARTIALLY IMPLEMENTED | FR-004; FR-005; FR-009; FR-013
BR-004 | Calculate historical and daily positions by date, book, counterparty, instrument, and currency. | Give trading users a reproducible inventory view. | Must | Daily signed net quantities reconcile to accepted trades and carry forward on expected sessions; source corrections update affected dates. | Validated trades; supported trading calendar | IMPLEMENTED | FR-006; FR-007; FR-009
BR-005 | Calculate daily position valuation and daily P&L. | Provide transparent daily equity valuation and trading P&L. | Must | Gold contains daily valuation and decomposed daily P&L; missing marks/baselines remain NULL with breaks; quantity changes are not misattributed to price movement. | Positions; validated price history; approved methodology | IMPLEMENTED | FR-007; FR-008; FR-009
BR-006 | Provide trading, P&L, and operational reporting. | Make outcomes and exceptions accessible to users. | Should | Read-only report/query surfaces expose run status, rejects, positions, P&L, and breaks; a dashboard is delivered only after user acceptance criteria are agreed. | Reporting requirements; Gold datasets | PARTIALLY IMPLEMENTED | FR-010; FR-011
BR-007 | Support operational monitoring, auditability, and error investigation. | Make failed and incomplete processing diagnosable. | Must | Every task attempt records status, timestamps, row counts, issue counts, and error details; valuation breaks and rejects retain lineage. | Audit and reject tables; operations ownership | PARTIALLY IMPLEMENTED | FR-005; FR-011; FR-012; FR-013
BR-008 | Automate repeatable daily processing with controlled reruns. | Reduce manual handling and support predictable delivery. | Must | A parameterized workflow executes the dependency graph; retry/rerun behavior is tested; production schedule remains disabled until readiness sign-off. | Production environment, source SLA, support model | PARTIALLY IMPLEMENTED | FR-012; FR-013

## Functional Req
FR ID | Parent BR | Functional description | Input | Processing logic | Expected output | Business rules | Error handling | Acceptance criteria | Components | Implementation status | Jira stories
FR-001 | BR-001 | Read the 14-column trade CSV from the configured Unity Catalog Volume as raw strings. | CSV snapshot at configured Volume path | Validate exact header, non-empty content, and structural integrity before write; remove identical in-batch rows. | cibc.bronze.trades snapshot with source_file, ingestion_timestamp, run_id | All source columns remain raw strings in Bronze; different trade versions remain distinct. | Fail before overwrite for bad header, empty file, corrupt row, or unreadable source; audit failure. | A valid fixture replaces Bronze with distinct raw rows and correct lineage; invalid fixtures leave the previous snapshot unchanged. | scripts/generate_trades.py; bronze/ingest_trades.py; UC Volume | IMPLEMENTED | TMP-011
FR-002 | BR-002 | Download daily unadjusted closing prices for requested tickers and inclusive date range. | Ticker/date parameters; yfinance public endpoint | Retry transient provider exceptions up to 3 attempts; normalize response shapes; record close, USD, source API, ingestion timestamp, run id. | cibc.bronze.market_prices | Default 10 configured symbols and seven-day lookback; no credentials currently used. | Fail on empty expected response, missing ticker, malformed or ambiguous response; no synthetic price is invented. | Fixture tests cover flat and MultiIndex payloads; missing expected sessions are surfaced. | bronze/ingest_prices.py; yfinance | IMPLEMENTED | TMP-013; TMP-014
FR-003 | BR-001 | Validate source schemas and convert raw values into typed Silver fields. | Bronze trades and prices | Use try_cast into DATE, TIMESTAMP, INT, DECIMAL(18,6), and preserve raw values in rejects. | Typed Silver trades/prices and reject tables | Financial amounts and quantities use DECIMAL; source IDs remain STRING. | Uncastable/invalid records are quarantined; incomplete expected price sessions prevent Silver merge. | Schema and cast tests verify typed values and preserve reason codes. | silver/process_trades.py; silver/process_prices.py | IMPLEMENTED | TMP-015; TMP-016
FR-004 | BR-003 | Select the highest trade version, then latest modified_timestamp, per trade_id. | Bronze trade snapshot | Reject exact duplicates; reject conflicting ties; do not fall back when the latest version is invalid or ambiguous. | At most one accepted Silver row per trade_id | Only trade IDs still in the new snapshot are removed when latest is unusable; absent IDs are not deleted from Silver. | Ambiguity and unorderable version are quarantined with reason codes. | Fixtures cover valid correction, exact duplicate, conflicting tie, invalid latest version, and lower version. | silver/process_trades.py; silver/trades_rejects | IMPLEMENTED | TMP-015; TMP-012
FR-005 | BR-007 | Apply trade and price data-quality rules and retain actionable rejects. | Raw trade and price records | Validate identifiers, mapping, side/quantity, positive prices, currency, dates/calendar, settlement, version, and price key uniqueness. | Silver accepted datasets, rejects with reason(s), valuation breaks | BUY is positive and SELL is negative; only USD and configured instruments are supported. | Reject invalid rows; fail task where missing expected prices make the requested output incomplete. | Each configured invalid fixture maps to expected reason(s); reject merge is idempotent. | Silver processors; common/rejects.py; gold/break_report.py | IMPLEMENTED | TMP-015; TMP-016
FR-006 | BR-004 | Calculate daily and cumulative signed positions at the defined Gold grain. | Silver accepted trades | Aggregate daily buy/sell/net then cumulative SUM(quantity) over trading sessions by book/counterparty/instrument/currency. | cibc.gold.positions | Position key is valuation_date + book_id + counterparty_id + instrument_id + currency; short quantities are allowed. | Empty sources or duplicate price keys fail without publishing; source-scoped merge reconciles history. | Daily/cumulative quantities match independent aggregation including no-trade days and short/flat positions. | gold/build_positions.py; gold/positions | IMPLEMENTED | TMP-017
FR-007 | BR-005 | Value positions using same-day close in the same currency. | Gold positions; Silver prices | market_value = closing_position_quantity * closing_price at exact valuation date and currency. | Gold position closing_price and market_value; missing-price break | Missing close remains NULL; quantities are unaffected; a flat/no-activity position does not require a mark. | Missing non-flat position marks create OPEN valuation breaks. | Valuation matches independent Decimal calculation; missing close produces NULL and a break. | gold/build_positions.py; gold/valuation_breaks | IMPLEMENTED | TMP-017
FR-008 | BR-005 | Calculate daily equity P&L separating opening-position price movement from trade-day economics. | Gold positions; Silver trades; Silver price history | OpeningQty*(CurrentClose-PreviousClose) + (DailyNetQty*CurrentClose - SignedTradeConsideration); new positions with zero opening quantity use trade-day term only. | cibc.gold.daily_pnl with status and valuation inputs | Latest prior close is the previous baseline; current close is exact date. Missing required current/baseline price leaves daily_pnl NULL. | Create missing-current-price or missing-baseline break; never treat NULL as zero. | Independent test examples match; activity quantity changes do not create false opening-position P&L. | gold/calculate_daily_pnl.py; gold/daily_pnl | IMPLEMENTED | TMP-018
FR-009 | BR-003 | Retain historical accepted prices, reject history, audit/break history, and recompute affected Gold history after corrections. | Full Silver history and correction snapshot | Prices/rejects MERGE by business key; Gold recomputes full Silver history; changed business values update scoped Gold rows. | Historical Silver/Gold datasets and lineage | Bronze trades is only the latest snapshot; disappeared IDs are not purged from Silver; Gold delete scope cannot remove absent instruments/symbols. | Require reconciliation and manual remediation for missing historical scope; expose limitations. | Backdated correction updates affected dates; retention and deletion semantics are documented before production. | Bronze/Silver/Gold Delta tables; Delta history | PARTIALLY IMPLEMENTED | TMP-012; TMP-017; TMP-018
FR-010 | BR-006 | Provide read-only operational and business reporting over run logs, rejects, positions, P&L, and breaks. | Gold/Silver Delta tables and Jobs API | Existing notebook report and demo SQL show status, metrics, rejects, positions, P&L, breaks; proposed dashboard consumes curated Gold. | Notebook/SQL reporting now; dashboard dataset/view and dashboard proposed | Do not claim Databricks SQL dashboard exists; current report is notebook-based. | Report shows NOT AVAILABLE when audit/API data is absent rather than inventing metrics. | Users reconcile report totals to tables; dashboard acceptance criteria and audience approved before build. | notebooks/02_pipeline_report.py; docs/demo_queries.sql; proposed dashboard | PARTIALLY IMPLEMENTED | TMP-019; TMP-020
FR-011 | BR-007 | Audit each task attempt with run/task identity, timing, status, counts, issues, and error details. | Databricks job/task context and module metrics | MERGE STARTED, metrics, SUCCESS/FAILED by run_id + task_run_id. | cibc.gold.pipeline_run_log; valuation_breaks; Silver reject tables | Audit persistence failure fails the task; audit currently omits insert/update/delete/rejects_written counters. | Capture exception type/message; if audit write itself fails log secondary exception. | Success and failure paths produce expected audit record; sensitive exception content reviewed before prod. | trade_pipeline/audit.py; break_report.py; report notebook | PARTIALLY IMPLEMENTED | TMP-019; TMP-024
FR-012 | BR-008 | Orchestrate six parameterized tasks with parallel source branches and dependency joins. | Databricks Job parameters | ingest_prices→process_prices and ingest_trades→process_trades run independently; build_positions joins both; calculate_daily_pnl follows. | Databricks Workflow run | max_concurrent_runs=1; weekday 18:00 America/New_York schedule is PAUSED; dev target only. | Workflow task failure blocks downstream; rerun through Jobs/CLI/notebook after investigation. | Bundle validation and a successful manual run confirm all six task dependencies and parameters. | jobs/resources/trade_pipeline.job.yml; databricks.yml; notebooks/01_run_pipeline.py | PARTIALLY IMPLEMENTED | TMP-009; TMP-010; TMP-023
FR-013 | BR-008 | Make reruns deterministic and recoverable for a fixed source snapshot and date range. | Same trade snapshot, ticker/date request, run parameters | Trade Bronze overwrite; price/Silver/Gold conditional MERGEs; reject/break writes are idempotent per identity/run. | Stable business keys/values and separate run audit history | A retry gets task attempt identity; full-history recompute is used; no partial input may delete outside source scope. | Fail-fast at bad input; inspect audit/reject/breaks, repair source, rerun; exact operational recovery time TBD. | Two complete identical end-to-end runs preserve business output and business keys; audit history records both. | Ingestion/processing modules; Databricks Workflow; audit | PARTIALLY IMPLEMENTED | TMP-016; TMP-022; TMP-024

## NFRs
NFR ID | Quality attribute | Acceptance target | Status | Evidence / gap
NFR-01 | Performance | PROPOSED: process the documented 1,200-trade / 10-symbol demonstration workload within 15 minutes end-to-end, excluding provider outages. | TO BE CONFIRMED | No measured run duration/SLA recorded in docs/test_results.md.
NFR-02 | Reliability | PROPOSED: >=99% successful scheduled runs per calendar month after production support and alerting are established. | TO BE CONFIRMED | Only a dev job is configured; schedule paused.
NFR-03 | Idempotency | PROPOSED: two runs over identical inputs produce identical business keys and financial values; only run-level audit/break history may grow. | PARTIALLY IMPLEMENTED | Unit tests cover scoped writes; documented second Databricks run was queued, not verified.
NFR-04 | Security | PROPOSED: job service principal has least privilege on cibc schemas and input Volume; secrets never stored in source control; access reviewed before non-dev deploy. | TO BE CONFIRMED | Grant template exists; principal/environment are placeholders.
NFR-05 | Maintainability | PROPOSED: source modules remain separated by Bronze/Silver/Gold; new business rules have unit tests and documented owners. | PARTIALLY IMPLEMENTED | Layered Python package and tests exist; CI/ownership not evidenced.
NFR-06 | Testability | PROPOSED: deterministic unit tests for rules; Spark integration tests for MERGE/Delta behavior; UAT evidence for financial outputs. | PARTIALLY IMPLEMENTED | pytest tests exist; PySpark/Java/Delta runtime availability is not confirmed locally.
NFR-07 | Scalability | PROPOSED: benchmark 100,000 trades and 50 symbols; confirm runtime and compute cost before adopting an incremental design. | TO BE CONFIRMED | Full-history recompute is documented as a prototype limitation; no benchmark.
NFR-08 | Observability | PROPOSED: detect failed run and notify support within 5 minutes; audit every task attempt; reconcile expected task count. | PARTIALLY IMPLEMENTED | Delta audit/reject/break data and report notebook; no automated alerting.
NFR-09 | Deployability | PROPOSED: repeatable Bundle validate/deploy in isolated dev/test/prod targets with reviewable configuration and smoke test. | PARTIALLY IMPLEMENTED | Databricks Asset Bundle has dev target and deploy script; no CI or non-dev target.
NFR-10 | Retention and recovery | TBD by data owner: approve retention, RTO, RPO, and source replay window before production. No numeric policy is assumed. | TO BE CONFIRMED | Not specified in repository.

## Data Sources
Source ID | Source | Status | System/provider | Format/interface | Location | Frequency | Volume | Business key | Version/correction | Quality rules | Ingestion strategy | Failure handling | Open decisions
SRC-TRADE | Trade transactions | IMPLEMENTED (synthetic prototype source) | scripts/generate_trades.py; no upstream trade system integration evidenced | CSV, 14 named columns; raw values landed as STRING | Local data/dirty_trades.csv then /Volumes/cibc/bronze/trade_files/dirty_trades.csv | Full snapshot per Job run; weekday schedule configured but paused; file delivery SLA TBD | Checked-in sample has 1,200 generated rows per docs/test_results.md; production volumes TBD | trade_id is logical entity; version + modified_timestamp select the latest; Bronze has no enforced PK | Highest version, then latest modified_timestamp; invalid/ambiguous latest is not replaced by older version | Nonblank IDs; configured instrument/symbol match; BUY/SELL; nonzero quantity; positive price; USD; valid timestamps/dates; supported NYSE session; settlement next session; version > 0 | Validate exact header/nonempty/structure; dedupe identical in-batch rows; INSERT OVERWRITE Bronze snapshot | Fail before overwrite; audit failure; Silver quarantines business-invalid rows | Real source owner, legal entity/system, delivery format contract, completeness watermark, file naming, correction/deletion semantics, volume/SLA, retention and access classification.
SRC-PRICE | Daily market prices | IMPLEMENTED (prototype provider; not approved for banking production) | Yahoo Finance via yfinance.download; provider rights/approval unverified | Python provider response normalized to symbol, price_date, close, currency | Provider response to cibc.bronze.market_prices Delta | Daily interval; seven-day default lookback; schedule is paused | 10 hard-coded default tickers; volume/limits and broader universe TBD | symbol + price_date (logical business key) | Latest ingestion_timestamp then run_id; conflicting tied payloads rejected | Expected NYSE sessions; non-future date; finite positive close; USD; unique symbol/date; completeness required | Retry up to three attempts; unadjusted Close; Bronze conditional MERGE | No data/omitted symbol/expected missing session fails; no stale close substituted for position valuation | Market-data owner/provider approval and license, adjustment/close definition, correction policy, availability SLA, symbol mapping, market calendar and missing-data escalation.
SRC-REF | Minimal reference data | PARTIALLY IMPLEMENTED (in-code mappings only) | trade_pipeline/config.py INSTRUMENT_ID_TO_SYMBOL; books/counterparties arrive as input strings | Python dictionary and input attributes; no reference Delta tables | Code configuration; no independent reference-data store | Release-time mapping update; business owner/update cadence TBD | 10 configured instrument-symbol pairs; book/counterparty cardinalities unknown | instrument_id; symbol mapping; book_id and counterparty_id are opaque strings | No effective-dated reference history | Configured instrument/symbol match; book/counterparty nonblank; USD-only currency | No separate pipeline; Silver validates against configured mapping | Unknown/mismatched instrument is rejected | Reference-data ownership, effective dating, books/counterparties validation, and need for persisted mappings must be confirmed.

## Data Dictionary
Catalog | Schema | Table | Table purpose | Grain | Business/unique key assumption | Column | Databricks SQL type | Precision/scale | Nullable | Default | Description | Source field | Transformation | Data quality rule | Storage strategy | Write semantics | DDL file
cibc | bronze | market_prices | Raw price records | One symbol and price date | Logical: symbol + price_date; no enforced constraint | symbol | STRING | N/A | Yes | None declared | Market ticker symbol | CSV.symbol or configured instrument mapping | Normalized/validated against instrument map | Required; mapped and consistent | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/bronze/market_prices.sql
cibc | bronze | market_prices | Raw price records | One symbol and price date | Logical: symbol + price_date; no enforced constraint | price_date | STRING | N/A | Yes | None declared | Market price effective date | Provider date | try_cast to DATE | Expected supported session; not future | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/bronze/market_prices.sql
cibc | bronze | market_prices | Raw price records | One symbol and price date | Logical: symbol + price_date; no enforced constraint | close | STRING | N/A | Yes | None declared | Unadjusted daily closing price | Provider Close | try_cast to DECIMAL(18,6) | Required, finite, positive; currency USD | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/bronze/market_prices.sql
cibc | bronze | market_prices | Raw price records | One symbol and price date | Logical: symbol + price_date; no enforced constraint | currency | STRING | N/A | Yes | None declared | Financial reporting currency | Trade/price source | USD-only prototype | Required on core accepted/Gold data | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/bronze/market_prices.sql
cibc | bronze | market_prices | Raw price records | One symbol and price date | Logical: symbol + price_date; no enforced constraint | source_api | STRING | N/A | Yes | None declared | Price provider identifier | yfinance.download | Added by price adapter | Provider identity recorded; approved source TBD | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/bronze/market_prices.sql
cibc | bronze | market_prices | Raw price records | One symbol and price date | Logical: symbol + price_date; no enforced constraint | ingestion_timestamp | TIMESTAMP | N/A | Yes | None declared | Ingestion event timestamp | Pipeline runtime | current_timestamp or provider batch timestamp | Audit lineage | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/bronze/market_prices.sql
cibc | bronze | market_prices | Raw price records | One symbol and price date | Logical: symbol + price_date; no enforced constraint | run_id | STRING | N/A | Yes | None declared | Pipeline run identifier | Databricks Job run id | Passed to task and persisted | Required for lineage where source available | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/bronze/market_prices.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | trade_id | STRING | N/A | Yes | None declared | Trade identifier on valuation break | Silver trade | Nullable for instrument/date-level break | Nullable | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | counterparty_id | STRING | N/A | Yes | None declared | Counterparty identifier | CSV.counterparty_id | Preserved as STRING | Required/nonblank for accepted trade | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | instrument_id | STRING | N/A | Yes | None declared | Instrument identifier on position/break | Configured mapping or Silver trade | STRING | Required on accepted trade; nullable in break DDL | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | symbol | STRING | N/A | Yes | None declared | Market ticker symbol | CSV.symbol or configured instrument mapping | Normalized/validated against instrument map | Required; mapped and consistent | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | side | STRING | N/A | Yes | None declared | Source trade direction | CSV.side | Raw value retained in Bronze/reject; used to sign quantity | BUY or SELL | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | quantity | STRING | N/A | Yes | None declared | Trade or position quantity | CSV.quantity or Silver trades.quantity | DECIMAL(18,6); SELL is negative in Silver; aggregates use DECIMAL(28,6) | Nonzero; BUY positive; SELL negative after normalization | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | price | STRING | N/A | Yes | None declared | Trade execution price | CSV.price | try_cast to DECIMAL(18,6) | Required and > 0 | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | currency | STRING | N/A | Yes | None declared | Financial reporting currency | Trade/price source | USD-only prototype | Required on core accepted/Gold data | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | trade_timestamp | STRING | N/A | Yes | None declared | Trade event timestamp | CSV.trade_timestamp | try_cast to TIMESTAMP | Required; date must match trade_date | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | trade_date | STRING | N/A | Yes | None declared | Trade business date | CSV.trade_date | try_cast to DATE; drives daily position activity | Required; supported session and not future | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | settlement_date | STRING | N/A | Yes | None declared | Settlement business date | CSV.settlement_date | try_cast to DATE | Required; next supported business session in current rule | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | book_id | STRING | N/A | Yes | None declared | Trading book identifier | CSV.book_id | Passed as opaque STRING | Required/nonblank; book reference not persisted | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | version | STRING | N/A | Yes | None declared | Trade source version | CSV.version | try_cast to INT | Positive; latest version wins | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | modified_timestamp | STRING | N/A | Yes | None declared | Trade source correction timestamp | CSV.modified_timestamp | try_cast to TIMESTAMP | Required; not earlier than trade timestamp | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | source_file | STRING | N/A | Yes | None declared | Source path/file lineage | Input Volume path | Added at Bronze ingestion; propagated to Silver trade | Required lineage in Bronze; nullable in Silver DDL | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | ingestion_timestamp | TIMESTAMP | N/A | Yes | None declared | Ingestion event timestamp | Pipeline runtime | current_timestamp or provider batch timestamp | Audit lineage | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | bronze | trades | Raw latest trade CSV snapshot | One distinct source row per current file snapshot | No enforced key; source identity is trade fields + version | run_id | STRING | N/A | Yes | None declared | Pipeline run identifier | Databricks Job run id | Passed to task and persisted | Required for lineage where source available | No physical PK/partition/clustering; small prototype | INSERT OVERWRITE after structural validation | database/tables/bronze/trades.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | id | BIGINT GENERATED ALWAYS AS IDENTITY | N/A | Generated | None declared | Delta identity surrogate | Delta table engine | GENERATED ALWAYS AS IDENTITY | Not a business key; omitted from MERGE source | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | valuation_date | DATE | N/A | No | None declared | Date represented by position/P&L/break | Trade/calendar/price dates | DATE | Required in position and P&L | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | book_id | STRING | N/A | No | None declared | Trading book identifier | CSV.book_id | Passed as opaque STRING | Required/nonblank; book reference not persisted | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | symbol | STRING | N/A | No | None declared | Market ticker symbol | CSV.symbol or configured instrument mapping | Normalized/validated against instrument map | Required; mapped and consistent | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | currency | STRING | N/A | No | None declared | Financial reporting currency | Trade/price source | USD-only prototype | Required on core accepted/Gold data | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | opening_quantity | DECIMAL(28,6) | 28,6 | No | None declared | Position at start of valuation date | Closing quantity - daily net quantity | DECIMAL(28,6) | Not null | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | buy_quantity | DECIMAL(28,6) | 28,6 | No | None declared | Daily buy flow at P&L grain | Gold positions.daily_buy_quantity | Sum across counterparties; DECIMAL(28,6) | Not null | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | sell_quantity | DECIMAL(28,6) | 28,6 | No | None declared | Daily sell flow at P&L grain | Gold positions.daily_sell_quantity | Sum across counterparties; positive absolute amount | Not null | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | closing_quantity | DECIMAL(28,6) | 28,6 | No | None declared | Closing position at P&L grain | Gold positions.closing_position_quantity | Sum across counterparties | Not null | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | previous_close | DECIMAL(18,6) | 18,6 | Yes | None declared | Latest available close strictly before valuation date | Silver market_prices | As-of prior-date join; DECIMAL(18,6) | Nullable; required for nonzero opening position | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | current_close | DECIMAL(18,6) | 18,6 | Yes | None declared | Exact-date close | Silver market_prices | Join symbol/date/currency; DECIMAL(18,6) | Nullable; required for daily P&L | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | market_value | DECIMAL(38,6) | 38,6 | Yes | None declared | Position market value | Closing quantity * closing price | DECIMAL(38,6) | Nullable when close is missing | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | unrealized_pnl_proxy | DECIMAL(38,6) | 38,6 | Yes | None declared | Cumulative mark-to-market less signed trade consideration proxy | Gold valuation and trade cash flows | DECIMAL(38,6); includes realized effects and is not true unrealized P&L | Nullable when current valuation unavailable | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | daily_pnl | DECIMAL(38,6) | 38,6 | Yes | None declared | Daily simplified cash-equity P&L | Opening position, current/prior closes, signed trade cash flow | DECIMAL(38,6) | Nullable when required price/baseline unavailable | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | calculation_status | STRING | N/A | No | None declared | Completeness status for daily P&L row | Price/baseline availability | COMPLETE, MISSING_CURRENT_PRICE, MISSING_BASELINE | Required | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | run_id | STRING | N/A | Yes | None declared | Pipeline run identifier | Databricks Job run id | Passed to task and persisted | Required for lineage where source available | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | daily_pnl | Daily book/symbol P&L and valuation inputs | Date + book + symbol + currency | valuation_date + book_id + symbol + currency | calculated_at | TIMESTAMP | N/A | Yes | None declared | Calculation timestamp | Gold processor runtime | current_timestamp | Nullable in DDL | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/daily_pnl.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | id | BIGINT GENERATED ALWAYS AS IDENTITY | N/A | Generated | None declared | Delta identity surrogate | Delta table engine | GENERATED ALWAYS AS IDENTITY | Not a business key; omitted from MERGE source | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | run_id | STRING | N/A | Yes | None declared | Pipeline run identifier | Databricks Job run id | Passed to task and persisted | Required for lineage where source available | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | task_run_id | STRING | N/A | Yes | None declared | Databricks task attempt identifier | Task context | Task run plus execution count where available | Logical audit key with run_id | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | task_name | STRING | N/A | Yes | None declared | Workflow task name | Bundle task_key | Recorded by audited wrapper | Required by contract | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | run_date | DATE | N/A | Yes | None declared | UTC date task attempt started | started_at | Derived in audit helper | Required by contract | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | started_at | TIMESTAMP | N/A | Yes | None declared | Task attempt start timestamp | Audit helper UTC clock | datetime.now(timezone.utc) | Required by contract | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | finished_at | TIMESTAMP | N/A | Yes | None declared | Task attempt completion timestamp | Audit helper UTC clock | Set on success/failure | Nullable while STARTED | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | status | STRING | N/A | Yes | None declared | Break or task state | Pipeline | OPEN for valuation breaks; STARTED/SUCCESS/FAILED for audit | Required in business record | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | source_table | STRING | N/A | Yes | None declared | Logical source table/path | Task configuration | Recorded by audited wrapper | Nullable for external source | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | target_table | STRING | N/A | Yes | None declared | Logical output table | Task configuration | Recorded by audited wrapper | Nullable where not applicable | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | requested_tickers | BIGINT | N/A | Yes | None declared | Number of requested market symbols | Task metrics | Count of normalized symbols | Nullable for trade-only task | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | input_rows | BIGINT | N/A | Yes | None declared | Rows read/processed | Task metrics | Task-defined count; see audit contract | Nullable on task start/failure | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | output_rows | BIGINT | N/A | Yes | None declared | Rows accepted or produced | Task metrics | Task-defined count; not always writes | Nullable on task start/failure | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | rejected_rows | BIGINT | N/A | Yes | None declared | Rows rejected in scoped processing | Task metrics | Can count records with multiple reasons once | Nullable on task start/failure | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | duplicate_rows | BIGINT | N/A | Yes | None declared | Duplicate/version rows | Task metrics | Task-specific duplicate definition | Nullable on task start/failure | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | issue_counts | MAP<STRING, BIGINT> | N/A | Yes | None declared | Reason-to-count map | Task metrics | Map of issue reason to count | Nullable; reasons may exceed rejected row count | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | error_type | STRING | N/A | Yes | None declared | Exception class on failed attempt | Caught exception | type(error).__name__ | Nullable unless failed | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | pipeline_run_log | Task-attempt audit and row/error metrics | One Job task attempt | run_id + task_run_id | error_message | STRING | N/A | Yes | None declared | Exception summary on failed attempt | Caught exception | str(error); sensitivity review required | Nullable unless failed | No physical PK/partition/clustering | MERGE STARTED/metrics/SUCCESS or FAILED | database/tables/gold/pipeline_run_log.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | id | BIGINT GENERATED ALWAYS AS IDENTITY | N/A | Generated | None declared | Delta identity surrogate | Delta table engine | GENERATED ALWAYS AS IDENTITY | Not a business key; omitted from MERGE source | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | valuation_date | DATE | N/A | No | None declared | Date represented by position/P&L/break | Trade/calendar/price dates | DATE | Required in position and P&L | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | book_id | STRING | N/A | No | None declared | Trading book identifier | CSV.book_id | Passed as opaque STRING | Required/nonblank; book reference not persisted | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | counterparty_id | STRING | N/A | No | None declared | Counterparty identifier | CSV.counterparty_id | Preserved as STRING | Required/nonblank for accepted trade | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | instrument_id | STRING | N/A | No | None declared | Instrument identifier on position/break | Configured mapping or Silver trade | STRING | Required on accepted trade; nullable in break DDL | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | currency | STRING | N/A | No | None declared | Financial reporting currency | Trade/price source | USD-only prototype | Required on core accepted/Gold data | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | daily_buy_quantity | DECIMAL(28,6) | 28,6 | No | None declared | Daily sum of positive BUY quantities | Silver trades.quantity | Grouped by position grain/date; DECIMAL(28,6) | Not null; zero when no buys | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | daily_sell_quantity | DECIMAL(28,6) | 28,6 | No | None declared | Daily absolute sum of signed SELL quantities | Silver trades.quantity | Sum(abs(quantity)) for sells; DECIMAL(28,6) | Not null; zero when no sells | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | daily_net_quantity | DECIMAL(28,6) | 28,6 | No | None declared | Daily signed net trade quantity | Silver trades.quantity | SUM(signed quantity); DECIMAL(28,6) | Not null | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | closing_position_quantity | DECIMAL(28,6) | 28,6 | No | None declared | Cumulative closing position | Daily net quantity | Cumulative SUM over session timeline; DECIMAL(28,6) | Not null; may be negative | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | closing_price | DECIMAL(18,6) | 18,6 | Yes | None declared | Exact-date closing mark | Silver market_prices.close | Join symbol/date/currency; DECIMAL(18,6) | Nullable when no same-day close | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | market_value | DECIMAL(38,6) | 38,6 | Yes | None declared | Position market value | Closing quantity * closing price | DECIMAL(38,6) | Nullable when close is missing | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | run_id | STRING | N/A | Yes | None declared | Pipeline run identifier | Databricks Job run id | Passed to task and persisted | Required for lineage where source available | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | positions | Daily cumulative positions and same-day valuation | Date + book + counterparty + instrument + currency | valuation_date + book_id + counterparty_id + instrument_id + currency | calculated_at | TIMESTAMP | N/A | Yes | None declared | Calculation timestamp | Gold processor runtime | current_timestamp | Nullable in DDL | No physical PK/partition/clustering | Conditional scoped MERGE reconciliation | database/tables/gold/positions.sql
cibc | gold | valuation_breaks | Run-level missing price/baseline exceptions | Run + instrument + date + break type, or trade-level unpriced trade | run_id + nullable trade_id/instrument_id/date + break_type | id | BIGINT GENERATED ALWAYS AS IDENTITY | N/A | Generated | None declared | Delta identity surrogate | Delta table engine | GENERATED ALWAYS AS IDENTITY | Not a business key; omitted from MERGE source | No physical PK/partition/clustering | Insert-only MERGE; run history retained | database/tables/gold/valuation_breaks.sql
cibc | gold | valuation_breaks | Run-level missing price/baseline exceptions | Run + instrument + date + break type, or trade-level unpriced trade | run_id + nullable trade_id/instrument_id/date + break_type | run_id | STRING | N/A | Yes | None declared | Pipeline run identifier | Databricks Job run id | Passed to task and persisted | Required for lineage where source available | No physical PK/partition/clustering | Insert-only MERGE; run history retained | database/tables/gold/valuation_breaks.sql
cibc | gold | valuation_breaks | Run-level missing price/baseline exceptions | Run + instrument + date + break type, or trade-level unpriced trade | run_id + nullable trade_id/instrument_id/date + break_type | trade_id | STRING | N/A | Yes | None declared | Trade identifier on valuation break | Silver trade | Nullable for instrument/date-level break | Nullable | No physical PK/partition/clustering | Insert-only MERGE; run history retained | database/tables/gold/valuation_breaks.sql
cibc | gold | valuation_breaks | Run-level missing price/baseline exceptions | Run + instrument + date + break type, or trade-level unpriced trade | run_id + nullable trade_id/instrument_id/date + break_type | instrument_id | STRING | N/A | Yes | None declared | Instrument identifier on position/break | Configured mapping or Silver trade | STRING | Required on accepted trade; nullable in break DDL | No physical PK/partition/clustering | Insert-only MERGE; run history retained | database/tables/gold/valuation_breaks.sql
cibc | gold | valuation_breaks | Run-level missing price/baseline exceptions | Run + instrument + date + break type, or trade-level unpriced trade | run_id + nullable trade_id/instrument_id/date + break_type | valuation_date | DATE | N/A | Yes | None declared | Date represented by position/P&L/break | Trade/calendar/price dates | DATE | Required in position and P&L | No physical PK/partition/clustering | Insert-only MERGE; run history retained | database/tables/gold/valuation_breaks.sql
cibc | gold | valuation_breaks | Run-level missing price/baseline exceptions | Run + instrument + date + break type, or trade-level unpriced trade | run_id + nullable trade_id/instrument_id/date + break_type | break_type | STRING | N/A | Yes | None declared | Valuation exception category | Gold calculation | MISSING_MARKET_PRICE or MISSING_PNL_BASELINE | Required | No physical PK/partition/clustering | Insert-only MERGE; run history retained | database/tables/gold/valuation_breaks.sql
cibc | gold | valuation_breaks | Run-level missing price/baseline exceptions | Run + instrument + date + break type, or trade-level unpriced trade | run_id + nullable trade_id/instrument_id/date + break_type | break_description | STRING | N/A | Yes | None declared | Human-readable exception detail | Gold calculation | Constructed from book/instrument/date context | Required | No physical PK/partition/clustering | Insert-only MERGE; run history retained | database/tables/gold/valuation_breaks.sql
cibc | gold | valuation_breaks | Run-level missing price/baseline exceptions | Run + instrument + date + break type, or trade-level unpriced trade | run_id + nullable trade_id/instrument_id/date + break_type | detected_at | TIMESTAMP | N/A | Yes | None declared | Break detection timestamp | Gold processor runtime | current_timestamp | Required | No physical PK/partition/clustering | Insert-only MERGE; run history retained | database/tables/gold/valuation_breaks.sql
cibc | gold | valuation_breaks | Run-level missing price/baseline exceptions | Run + instrument + date + break type, or trade-level unpriced trade | run_id + nullable trade_id/instrument_id/date + break_type | status | STRING | N/A | Yes | None declared | Break or task state | Pipeline | OPEN for valuation breaks; STARTED/SUCCESS/FAILED for audit | Required in business record | No physical PK/partition/clustering | Insert-only MERGE; run history retained | database/tables/gold/valuation_breaks.sql
cibc | silver | market_prices | Validated daily closing prices | One symbol and price date | symbol + price_date; positive close CHECK | id | BIGINT GENERATED ALWAYS AS IDENTITY | N/A | Generated | None declared | Delta identity surrogate | Delta table engine | GENERATED ALWAYS AS IDENTITY | Not a business key; omitted from MERGE source | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/silver/market_prices.sql
cibc | silver | market_prices | Validated daily closing prices | One symbol and price date | symbol + price_date; positive close CHECK | symbol | STRING | N/A | No | None declared | Market ticker symbol | CSV.symbol or configured instrument mapping | Normalized/validated against instrument map | Required; mapped and consistent | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/silver/market_prices.sql
cibc | silver | market_prices | Validated daily closing prices | One symbol and price date | symbol + price_date; positive close CHECK | price_date | DATE | N/A | No | None declared | Market price effective date | Provider date | try_cast to DATE | Expected supported session; not future | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/silver/market_prices.sql
cibc | silver | market_prices | Validated daily closing prices | One symbol and price date | symbol + price_date; positive close CHECK | close | DECIMAL(18,6) | 18,6 | No | None declared | Unadjusted daily closing price | Provider Close | try_cast to DECIMAL(18,6) | Required, finite, positive; currency USD | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/silver/market_prices.sql
cibc | silver | market_prices | Validated daily closing prices | One symbol and price date | symbol + price_date; positive close CHECK | currency | STRING | N/A | No | None declared | Financial reporting currency | Trade/price source | USD-only prototype | Required on core accepted/Gold data | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/silver/market_prices.sql
cibc | silver | market_prices | Validated daily closing prices | One symbol and price date | symbol + price_date; positive close CHECK | source_api | STRING | N/A | Yes | None declared | Price provider identifier | yfinance.download | Added by price adapter | Provider identity recorded; approved source TBD | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/silver/market_prices.sql
cibc | silver | market_prices | Validated daily closing prices | One symbol and price date | symbol + price_date; positive close CHECK | ingestion_timestamp | TIMESTAMP | N/A | Yes | None declared | Ingestion event timestamp | Pipeline runtime | current_timestamp or provider batch timestamp | Audit lineage | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/silver/market_prices.sql
cibc | silver | market_prices | Validated daily closing prices | One symbol and price date | symbol + price_date; positive close CHECK | run_id | STRING | N/A | Yes | None declared | Pipeline run identifier | Databricks Job run id | Passed to task and persisted | Required for lineage where source available | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/silver/market_prices.sql
cibc | silver | market_prices | Validated daily closing prices | One symbol and price date | symbol + price_date; positive close CHECK | bronze_run_id | STRING | N/A | Yes | None declared | Bronze source run identifier | Bronze.run_id | Propagated selected-row lineage | Lineage may be nullable on historical rows | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/silver/market_prices.sql
cibc | silver | market_prices | Validated daily closing prices | One symbol and price date | symbol + price_date; positive close CHECK | bronze_ingestion_timestamp | TIMESTAMP | N/A | Yes | None declared | Bronze ingestion timestamp | Bronze.ingestion_timestamp | Propagated selected-row lineage | Lineage may be nullable on historical rows | No physical PK/partition/clustering | Conditional MERGE on symbol + price_date | database/tables/silver/market_prices.sql
cibc | silver | market_prices_rejects | Price data-quality rejects | One rejected price record/reason history row | Logical symbol/date/payload + reason | id | BIGINT GENERATED ALWAYS AS IDENTITY | N/A | Generated | None declared | Delta identity surrogate | Delta table engine | GENERATED ALWAYS AS IDENTITY | Not a business key; omitted from MERGE source | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/market_prices_rejects.sql
cibc | silver | market_prices_rejects | Price data-quality rejects | One rejected price record/reason history row | Logical symbol/date/payload + reason | symbol | STRING | N/A | Yes | None declared | Market ticker symbol | CSV.symbol or configured instrument mapping | Normalized/validated against instrument map | Required; mapped and consistent | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/market_prices_rejects.sql
cibc | silver | market_prices_rejects | Price data-quality rejects | One rejected price record/reason history row | Logical symbol/date/payload + reason | price_date | STRING | N/A | Yes | None declared | Market price effective date | Provider date | try_cast to DATE | Expected supported session; not future | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/market_prices_rejects.sql
cibc | silver | market_prices_rejects | Price data-quality rejects | One rejected price record/reason history row | Logical symbol/date/payload + reason | close | STRING | N/A | Yes | None declared | Unadjusted daily closing price | Provider Close | try_cast to DECIMAL(18,6) | Required, finite, positive; currency USD | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/market_prices_rejects.sql
cibc | silver | market_prices_rejects | Price data-quality rejects | One rejected price record/reason history row | Logical symbol/date/payload + reason | currency | STRING | N/A | Yes | None declared | Financial reporting currency | Trade/price source | USD-only prototype | Required on core accepted/Gold data | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/market_prices_rejects.sql
cibc | silver | market_prices_rejects | Price data-quality rejects | One rejected price record/reason history row | Logical symbol/date/payload + reason | source_api | STRING | N/A | Yes | None declared | Price provider identifier | yfinance.download | Added by price adapter | Provider identity recorded; approved source TBD | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/market_prices_rejects.sql
cibc | silver | market_prices_rejects | Price data-quality rejects | One rejected price record/reason history row | Logical symbol/date/payload + reason | ingestion_timestamp | TIMESTAMP | N/A | Yes | None declared | Ingestion event timestamp | Pipeline runtime | current_timestamp or provider batch timestamp | Audit lineage | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/market_prices_rejects.sql
cibc | silver | market_prices_rejects | Price data-quality rejects | One rejected price record/reason history row | Logical symbol/date/payload + reason | run_id | STRING | N/A | Yes | None declared | Pipeline run identifier | Databricks Job run id | Passed to task and persisted | Required for lineage where source available | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/market_prices_rejects.sql
cibc | silver | market_prices_rejects | Price data-quality rejects | One rejected price record/reason history row | Logical symbol/date/payload + reason | rejection_reason | STRING | N/A | Yes | None declared | One or more validation/reconciliation reason codes | Silver validation | Pipe-separated rule names | Required for reject record | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/market_prices_rejects.sql
cibc | silver | market_prices_rejects | Price data-quality rejects | One rejected price record/reason history row | Logical symbol/date/payload + reason | rejected_at | TIMESTAMP | N/A | Yes | None declared | Reject capture timestamp | Silver processor runtime | current_timestamp | Required for reject record | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/market_prices_rejects.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | id | BIGINT GENERATED ALWAYS AS IDENTITY | N/A | Generated | None declared | Delta identity surrogate | Delta table engine | GENERATED ALWAYS AS IDENTITY | Not a business key; omitted from MERGE source | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | trade_id | STRING | N/A | No | None declared | Trade identifier on valuation break | Silver trade | Nullable for instrument/date-level break | Nullable | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | counterparty_id | STRING | N/A | No | None declared | Counterparty identifier | CSV.counterparty_id | Preserved as STRING | Required/nonblank for accepted trade | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | instrument_id | STRING | N/A | No | None declared | Instrument identifier on position/break | Configured mapping or Silver trade | STRING | Required on accepted trade; nullable in break DDL | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | symbol | STRING | N/A | No | None declared | Market ticker symbol | CSV.symbol or configured instrument mapping | Normalized/validated against instrument map | Required; mapped and consistent | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | quantity | DECIMAL(18,6) | 18,6 | No | None declared | Trade or position quantity | CSV.quantity or Silver trades.quantity | DECIMAL(18,6); SELL is negative in Silver; aggregates use DECIMAL(28,6) | Nonzero; BUY positive; SELL negative after normalization | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | price | DECIMAL(18,6) | 18,6 | No | None declared | Trade execution price | CSV.price | try_cast to DECIMAL(18,6) | Required and > 0 | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | currency | STRING | N/A | No | None declared | Financial reporting currency | Trade/price source | USD-only prototype | Required on core accepted/Gold data | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | trade_date | DATE | N/A | No | None declared | Trade business date | CSV.trade_date | try_cast to DATE; drives daily position activity | Required; supported session and not future | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | settlement_date | DATE | N/A | No | None declared | Settlement business date | CSV.settlement_date | try_cast to DATE | Required; next supported business session in current rule | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | book_id | STRING | N/A | No | None declared | Trading book identifier | CSV.book_id | Passed as opaque STRING | Required/nonblank; book reference not persisted | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | version | INT | N/A | No | None declared | Trade source version | CSV.version | try_cast to INT | Positive; latest version wins | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | modified_timestamp | TIMESTAMP | N/A | No | None declared | Trade source correction timestamp | CSV.modified_timestamp | try_cast to TIMESTAMP | Required; not earlier than trade timestamp | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | bronze_run_id | STRING | N/A | Yes | None declared | Bronze source run identifier | Bronze.run_id | Propagated selected-row lineage | Lineage may be nullable on historical rows | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | bronze_ingestion_timestamp | TIMESTAMP | N/A | Yes | None declared | Bronze ingestion timestamp | Bronze.ingestion_timestamp | Propagated selected-row lineage | Lineage may be nullable on historical rows | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades | Validated current trade versions | One accepted row per trade_id | trade_id | source_file | STRING | N/A | Yes | None declared | Source path/file lineage | Input Volume path | Added at Bronze ingestion; propagated to Silver trade | Required lineage in Bronze; nullable in Silver DDL | No physical PK/partition/clustering | Conditional MERGE; unusable present IDs removed | database/tables/silver/trades.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | id | BIGINT GENERATED ALWAYS AS IDENTITY | N/A | Generated | None declared | Delta identity surrogate | Delta table engine | GENERATED ALWAYS AS IDENTITY | Not a business key; omitted from MERGE source | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | trade_id | STRING | N/A | Yes | None declared | Trade identifier on valuation break | Silver trade | Nullable for instrument/date-level break | Nullable | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | counterparty_id | STRING | N/A | Yes | None declared | Counterparty identifier | CSV.counterparty_id | Preserved as STRING | Required/nonblank for accepted trade | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | instrument_id | STRING | N/A | Yes | None declared | Instrument identifier on position/break | Configured mapping or Silver trade | STRING | Required on accepted trade; nullable in break DDL | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | symbol | STRING | N/A | Yes | None declared | Market ticker symbol | CSV.symbol or configured instrument mapping | Normalized/validated against instrument map | Required; mapped and consistent | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | side | STRING | N/A | Yes | None declared | Source trade direction | CSV.side | Raw value retained in Bronze/reject; used to sign quantity | BUY or SELL | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | quantity | STRING | N/A | Yes | None declared | Trade or position quantity | CSV.quantity or Silver trades.quantity | DECIMAL(18,6); SELL is negative in Silver; aggregates use DECIMAL(28,6) | Nonzero; BUY positive; SELL negative after normalization | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | price | STRING | N/A | Yes | None declared | Trade execution price | CSV.price | try_cast to DECIMAL(18,6) | Required and > 0 | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | currency | STRING | N/A | Yes | None declared | Financial reporting currency | Trade/price source | USD-only prototype | Required on core accepted/Gold data | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | trade_timestamp | STRING | N/A | Yes | None declared | Trade event timestamp | CSV.trade_timestamp | try_cast to TIMESTAMP | Required; date must match trade_date | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | trade_date | STRING | N/A | Yes | None declared | Trade business date | CSV.trade_date | try_cast to DATE; drives daily position activity | Required; supported session and not future | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | settlement_date | STRING | N/A | Yes | None declared | Settlement business date | CSV.settlement_date | try_cast to DATE | Required; next supported business session in current rule | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | book_id | STRING | N/A | Yes | None declared | Trading book identifier | CSV.book_id | Passed as opaque STRING | Required/nonblank; book reference not persisted | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | version | STRING | N/A | Yes | None declared | Trade source version | CSV.version | try_cast to INT | Positive; latest version wins | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | modified_timestamp | STRING | N/A | Yes | None declared | Trade source correction timestamp | CSV.modified_timestamp | try_cast to TIMESTAMP | Required; not earlier than trade timestamp | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | source_file | STRING | N/A | Yes | None declared | Source path/file lineage | Input Volume path | Added at Bronze ingestion; propagated to Silver trade | Required lineage in Bronze; nullable in Silver DDL | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | ingestion_timestamp | TIMESTAMP | N/A | Yes | None declared | Ingestion event timestamp | Pipeline runtime | current_timestamp or provider batch timestamp | Audit lineage | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | run_id | STRING | N/A | Yes | None declared | Pipeline run identifier | Databricks Job run id | Passed to task and persisted | Required for lineage where source available | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | rejection_reason | STRING | N/A | Yes | None declared | One or more validation/reconciliation reason codes | Silver validation | Pipe-separated rule names | Required for reject record | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql
cibc | silver | trades_rejects | Trade data-quality and version rejects | One rejected raw record/reason history row | Logical reject key from business columns + source file + reason | rejected_at | TIMESTAMP | N/A | Yes | None declared | Reject capture timestamp | Silver processor runtime | current_timestamp | Required for reject record | No physical PK/partition/clustering | Insert-once MERGE reject history | database/tables/silver/trades_rejects.sql

## Epics
Planning ID | Epic name | Priority | Jira status | Scope note
TMP-EP01 | Project Mobilisation and Business Requirements | High | To Do | Planning epic; mixed current-state evidence and target backlog. See linked story implementation status.
TMP-EP02 | Architecture, Data Contracts and Governance Design | High | To Do | Planning epic; mixed current-state evidence and target backlog. See linked story implementation status.
TMP-EP03 | Platform Engineering and CI/CD | High | To Do | Planning epic; mixed current-state evidence and target backlog. See linked story implementation status.
TMP-EP04 | Trade and Market Data Integration | High | To Do | Planning epic; mixed current-state evidence and target backlog. See linked story implementation status.
TMP-EP05 | Positions and Daily P&L | High | To Do | Planning epic; mixed current-state evidence and target backlog. See linked story implementation status.
TMP-EP06 | Testing, Reconciliation and Reporting | High | To Do | Planning epic; mixed current-state evidence and target backlog. See linked story implementation status.
TMP-EP07 | Release Readiness and Operational Handover | High | To Do | Planning epic; mixed current-state evidence and target backlog. See linked story implementation status.

## Stories
Planning ID | Epic ID | Story title | User story / objective | Detailed description | Acceptance criteria | Story points | Priority | Implementation status | Sprint | BR IDs | FR IDs | Predecessor stories | Required inputs | Expected outputs
TMP-001 | TMP-EP01 | Baseline current implementation and confirm scope | Record verified capabilities, limitations, stakeholders, assumptions, and prototype-versus-production boundaries. | Use repository modules, DDL, tests, Bundle, and dated run evidence to approve the first scope baseline. Do not describe proposed controls as deployed. | Inventory covers all six workflow tasks, 10 physical tables, two notebooks, Bundle targets, and test evidence.; Every capability is labelled implemented, partial, planned, or to be confirmed with a repository evidence reference.; Business owner confirms prototype scope and named decision owners before Sprint 2 exit. | 2 | High | PARTIALLY IMPLEMENTED | Sprint 1 | BR-001; BR-008 | FR-012 |  | Repository; product/operations contacts | Approved scope and implementation inventory
TMP-002 | TMP-EP01 | Approve business and functional requirements | Turn current capabilities and business needs into testable BR/FR acceptance criteria. | Confirm user roles, daily business outputs, timing, correction semantics, report needs, and sign-off owners. Link BR-001..008 to FR-001..013. | All eight business requirements have an owner, priority, acceptance evidence, and dependency.; All 13 functional requirements identify input, processing, output, business rule, and failure behavior.; Product owner records decisions or explicit TBDs; no unsupported policy is silently assumed. | 3 | High | PLANNED | Sprint 1 | BR-001; BR-002; BR-003; BR-004; BR-005; BR-006; BR-007; BR-008 | FR-001; FR-002; FR-003; FR-004; FR-005; FR-006; FR-007; FR-008; FR-009; FR-010; FR-011; FR-012; FR-013 | TMP-001 | Implementation inventory; business/operations interviews | Signed requirements and acceptance criteria
TMP-003 | TMP-EP01 | Set measurable non-functional and operational targets | Agree performance, availability, support, security, retention, RTO/RPO, and recovery targets. | Use proposed thresholds as discussion points only. Confirm owner, measurement window, and evidence for each target. | NFR-01..10 each has a confirmed target or named owner and due date for TBD.; Performance baseline includes representative row counts, symbols, runtime, and cost.; Retention, access classification, RTO/RPO, support hours, and alert response are approved or explicitly excluded from prototype. | 2 | High | PLANNED | Sprint 1 | BR-007; BR-008 | FR-011; FR-012; FR-013 | TMP-002 | Business/technology policy owners; proposed NFRs | Approved NFR baseline
TMP-004 | TMP-EP02 | Document and validate existing solution architecture | Establish an evidence-backed architecture baseline and component responsibilities. | Document Unity Catalog, Delta layers, Python wheel, Job, notebooks, audit/rejects, and current deployment path. | Current architecture matches databricks.yml, job YAML, source modules, and DDL.; Trade/price parallel branches and join dependencies are accurate.; Current provider, paused schedule, dev-only target, and notebook reporting are labelled as implemented/current limitations. | 3 | High | IMPLEMENTED |  | BR-001; BR-002; BR-004; BR-005; BR-007; BR-008 | FR-006; FR-008; FR-011; FR-012 |  | Repository implementation | Current-state architecture
TMP-005 | TMP-EP02 | Approve target security and environment architecture | Define deployable dev/test/prod boundaries and least-privilege runtime identity. | Design only what is supported by actual workspace controls; confirm environment availability, principals, grants, networking, and secrets approach. | Environment promotion and job identity are approved by platform owner.; Unity Catalog grants cover required schemas and Volume only; no secrets are committed.; Architecture labels all unprovisioned targets and controls as proposed. | 3 | High | PLANNED | Sprint 2 | BR-007; BR-008 | FR-011; FR-012 | TMP-002; TMP-003; TMP-004 | Workspace/platform/security owner decisions | Approved environment and access design
TMP-006 | TMP-EP02 | Confirm trade source contract and snapshot semantics | Make source ownership, completeness, corrections, and deletion semantics explicit. | Current input is synthetic; define the future producer contract and safe transition from full snapshot to an authoritative feed. | Trade source owner, file schema, delivery cutoff, completeness marker, and correction/deletion semantics are recorded.; A missing trade in a later snapshot is not treated as a cancellation without explicit business rule.; Sample volume, retention, privacy classification, and replay window are approved or tracked as TBD. | 2 | High | PARTIALLY IMPLEMENTED | Sprint 1 | BR-001; BR-003 | FR-001; FR-004; FR-009 |  | Synthetic CSV; trade owner | Trade source specification
TMP-007 | TMP-EP02 | Select and approve market-data source | Resolve whether Yahoo Finance is acceptable for the prototype and choose a licensed production source. | Confirm price type, currency, adjustments, symbol universe, rights, correction policy, availability, and missing-price escalation; synthetic fixtures are acceptable for deterministic tests only. | Provider and business owner approve data rights and use case before production.; Price-date/price-type/currency contract and correction policy are documented.; Daily availability and expected-session completeness thresholds have named owners. | 3 | High | PLANNED | Sprint 2 | BR-002; BR-005 | FR-002; FR-005; FR-007; FR-008 | TMP-002 | Current yfinance adapter; market-data owner | Approved source decision and interface contract
TMP-008 | TMP-EP02 | Approve physical data dictionary and retention model | Review all current table grains, keys, financial types, lineage, and future retention needs. | Use the 10 physical DDL files as current-state truth; identify no enforced primary keys and no dedicated reference/reporting tables. | Data dictionary lists every column and exact DDL type/nullability for all 10 tables.; Business owner approves table grain and logical key assumptions.; Partitioning/clustering remains absent unless measured query patterns justify it.; Retention and Delta cleanup policy are approved before any production purge/optimization. | 2 | High | NOT VERIFIED | Sprint 5 | BR-003; BR-004; BR-005; BR-007 | FR-003; FR-006; FR-007; FR-008; FR-009; FR-011 | TMP-006; TMP-007 | database/tables DDL; provider/trade contracts | Approved dictionary and data-retention decisions
TMP-009 | TMP-EP03 | Maintain reproducible Databricks Asset Bundle development deployment | Validate current development Bundle build and deploy path. | Bundle builds a wheel and deploys the six-task job/notebooks to the dev target; schedule remains paused by configuration. | Bundle validation succeeds with the documented dev target and CLI profile.; Wheel contains all six entry points and deploy uses repository source.; Manual smoke run evidence is attached; no production readiness is inferred. | 3 | High | IMPLEMENTED |  | BR-008 | FR-012 |  | databricks.yml; job resource; scripts/deploy.sh | Validated dev deployment procedure
TMP-010 | TMP-EP03 | Add reviewed CI checks and controlled deployment promotion | Automate deterministic tests, Bundle validation, and reviewed artifact promotion. | Create CI using existing pytest/package/Bundle checks; add non-dev targets only after platform provisioning and identity approval. | Pull request CI runs deterministic local tests and Bundle validation without credentials in logs.; Deployment artifact/version is traceable to reviewed source revision.; Promotion cannot unpause a schedule or deploy to an unapproved target without explicit approval. | 5 | High | PLANNED | Sprint 3 | BR-007; BR-008 | FR-012; FR-013 | TMP-005; TMP-009 | Approved environment/security design; current Bundle | CI workflow and controlled deploy procedure
TMP-011 | TMP-EP04 | Ingest synthetic trade snapshot into Bronze | Load structurally valid trade snapshots with deterministic raw lineage. | Current implementation validates the 14-field CSV and atomically overwrites Bronze after input checks. | Exact schema, empty-file, and malformed-row cases are tested.; Identical in-batch records are removed; versions of a trade remain present.; Invalid file never overwrites existing Bronze; valid rerun yields same business rows. | 5 | High | IMPLEMENTED |  | BR-001; BR-003 | FR-001; FR-013 | TMP-006 | CSV snapshot in UC Volume | cibc.bronze.trades
TMP-012 | TMP-EP04 | Resolve trade snapshot disappearance and historical correction controls | Prevent a source snapshot replacement from leaving stale or silently deleting trades. | Current Bronze retains only latest snapshot and Silver does not remove trade IDs absent from a later file. Choose event/history storage or safe snapshot reconciliation. | Trade owner approves semantics for missing trade IDs, cancellation, and correction.; A two-snapshot test proves accepted Silver matches the agreed authoritative source state.; Backdated corrections are traceable and recompute the intended history without unrelated deletes. | 5 | High | PLANNED | Sprint 3 | BR-003; BR-004; BR-005 | FR-004; FR-009; FR-013 | TMP-006; TMP-011 | Approved trade source semantics; current Bronze/Silver behavior | Versioned history/reconciliation design and tested implementation
TMP-013 | TMP-EP04 | Ingest and retain daily market-price history | Load supported daily close records with source identity and repeatable keys. | Current adapter calls Yahoo Finance, stores unadjusted closes, retries transient failures, and merges Bronze on symbol/date. | Default symbols, date boundaries, provider response variants, NaN, duplicate keys, and retry errors have deterministic tests.; Price rows carry source, currency, ingestion timestamp, and run lineage.; Provider limitations and data rights are explicit in the source contract. | 5 | High | IMPLEMENTED |  | BR-002 | FR-002; FR-013 | TMP-007 | Daily price provider response | cibc.bronze.market_prices
TMP-014 | TMP-EP04 | Harden price source decision and completeness exception process | Make price completeness and manual resolution operationally actionable. | Use provider choice from TMP-007; define approved synthetic fixtures for test environments and operational handling for late/missing prices. | Missing expected session is tied to symbol/date and owner; no stale price is used for position valuation.; Test fixtures are deterministic and cannot be mistaken for production source data.; Approved provider/credentials, rate limits, correction policy, and retries are configured outside source code where required. | 3 | High | PLANNED | Sprint 5 | BR-002; BR-005; BR-007 | FR-002; FR-005; FR-007; FR-013 | TMP-007; TMP-013 | Approved provider decision; current completeness checks | Price-source controls and exception runbook
TMP-015 | TMP-EP04 | Validate Silver trades and prices with reject history | Publish typed records only after business validation and deterministic version selection. | Current code performs typed conversion, configured business checks, deduplication/versioning, conditional merge, and reject-history writes. | Trade and price fixtures cover configured rules and reason codes.; Silver trade business key is trade_id; price key is symbol + price_date.; Reject writes are idempotent and preserve raw source fields/lineage; missing expected price blocks Silver update. | 5 | High | IMPLEMENTED |  | BR-003; BR-007 | FR-003; FR-004; FR-005; FR-013 | TMP-011; TMP-013 | Bronze trades and prices | Silver validated tables and rejects
TMP-016 | TMP-EP06 | Run Spark/Delta integration and end-to-end rerun validation | Prove Delta writes, constraints, lineage, recovery, and same-input idempotency in a supported runtime. | Local Spark availability is not evidenced; docs/test_results.md records a successful dated pipeline run but its same-parameter second run was queued. | Spark/Delta integration suite runs in a supported CI or Databricks test environment and results are retained.; A second complete run with the same inputs verifies stable business keys/values and expected audit history growth.; Failure injection confirms no unsafe publication and a documented rerun recovers the task. | 2 | High | PLANNED | Sprint 4 | BR-003; BR-007; BR-008 | FR-003; FR-005; FR-009; FR-013 | TMP-015 | Supported Spark/Delta environment; current test suite | Integration, idempotency, and recovery evidence
TMP-017 | TMP-EP05 | Build cumulative daily positions and exact-date valuation | Publish historical positions at the agreed book/counterparty/instrument/date grain. | Current implementation aggregates signed trade quantities, carries positions across trading sessions, and joins same-day same-currency marks. | Position grain and key match the approved dictionary.; Daily buys, sells, net, closing quantity, close, and market value reconcile to independent calculations.; Missing same-day price leaves price/value NULL and creates a break without changing quantity. | 5 | High | IMPLEMENTED |  | BR-004; BR-005 | FR-006; FR-007; FR-009 | TMP-015 | Silver trades and prices | cibc.gold.positions; position valuation breaks
TMP-018 | TMP-EP05 | Calculate daily cash-equity mark-to-market P&L | Separate opening position market move from trade-day economic P&L. | Current Gold formula uses prior close for opening inventory and signed trade consideration for intraday activity; cumulative proxy is not true unrealized P&L. | Daily output grain is valuation_date + book_id + symbol + currency.; Price movement and trade-day terms reconcile independently, including sells, new/flat positions, prior-close baseline, and missing prices.; unrealized_pnl_proxy is clearly labelled as a cumulative proxy and is not presented as true unrealized P&L. | 5 | High | IMPLEMENTED |  | BR-005 | FR-007; FR-008; FR-009 | TMP-017 | Gold positions; Silver trades/prices | cibc.gold.daily_pnl; P&L breaks
TMP-019 | TMP-EP06 | Provide notebook and SQL operational reporting | Expose current job run, audit metrics, rejections, positions, P&L, and valuation breaks. | A run-trigger notebook, read-only report notebook, and demo SQL exist. No deployed dashboard is evidenced. | Run report identifies audit-derived status and clearly marks unavailable counts.; Notebook output is read-only and totals reconcile to source tables.; Report states that scheduled-run completeness is not evaluated and dashboard is not implemented. | 3 | Medium | IMPLEMENTED |  | BR-006; BR-007; BR-008 | FR-010; FR-011; FR-012 | TMP-018 | Gold/Silver tables and Jobs API | Run-control/report notebooks and SQL queries
TMP-020 | TMP-EP06 | Deliver user-accepted trading and P&L dashboard MVP | Present agreed Gold reporting datasets in an approved Databricks SQL dashboard or chosen BI tool. | Dashboard technology, user roles, filters, reconciliation views, and access model remain to be confirmed; this is proposed work, not current functionality. | Product owner signs off audience, filters, date/book/symbol dimensions, and exception drill-through.; Dashboard totals reconcile to Gold daily_pnl and positions for agreed test dates.; Dashboard access is least privilege and deployment is repeatable; no dashboard is reported as live before sign-off. | 5 | Medium | BLOCKED | Sprint 5 | BR-006 | FR-010 | TMP-002; TMP-008; TMP-018; TMP-019 | Approved reporting requirements; Gold datasets | Dashboard MVP and validation evidence
TMP-021 | TMP-EP06 | Maintain deterministic unit and transformation tests | Protect module contracts and calculation rules with repeatable test cases. | Tests cover source parsing, transformations, DDL/query shape, packaging, notebook helpers, and financial examples; Spark-dependent cases need a compatible runtime. Three focused tests currently fail because they reference removed Silver *_constraints.sql files; current checks are consolidated into trades.sql and market_prices.sql. | Business-rule tests include correction, duplicate, calendar, missing price, short position, and P&L decomposition cases.; CI reports skips separately from passes and does not treat unavailable Spark tests as verified.; Replace stale test references with the consolidated Silver DDL and verify its CHECK constraints.; New failures are triaged against the baseline; no unrelated failures are silently waived. | 3 | High | PARTIALLY IMPLEMENTED | Sprint 4 | BR-001; BR-002; BR-003; BR-004; BR-005; BR-007 | FR-001; FR-002; FR-003; FR-004; FR-005; FR-006; FR-007; FR-008 |  | pytest suite; supported Python/Spark runtime | Deterministic test evidence
TMP-022 | TMP-EP06 | Complete independent position/P&L reconciliation and UAT | Close the gap between pipeline output and business-approved calculations. | The 2026-10-11 run has independent SQL reconciliation with zero reported mismatches; same-input rerun remained queued in the report. | Trade-to-position quantities reconcile by date/book/counterparty/instrument.; Position market value and daily P&L reconcile using approved close/baseline/trade cash-flow methodology.; Business owner signs UAT evidence for representative long, short, flat, correction, and missing-price cases.; A complete same-input rerun has recorded evidence; do not rely only on unit tests. | 2 | High | PARTIALLY IMPLEMENTED | Sprint 4 | BR-003; BR-004; BR-005; BR-006 | FR-006; FR-007; FR-008; FR-009; FR-010; FR-013 | TMP-016; TMP-018 | Gold outputs; independent SQL; business test cases | Reconciliation and UAT sign-off
TMP-023 | TMP-EP07 | Operate the dev workflow with controlled scheduling | Use existing Asset Bundle workflow safely and keep schedule gated on readiness. | Current Job allows one concurrent run, runs six tasks, and has a weekday 18:00 America/New_York schedule configured as PAUSED. | Manual run and failure states are visible in Job UI and audit tables.; Schedule remains paused until source owner, support contact, permissions, runbook, and alert path are approved.; Any future unpause/change is reviewed and recorded with owner and rollback path. | 3 | High | PARTIALLY IMPLEMENTED | Sprint 2 | BR-007; BR-008 | FR-011; FR-012; FR-013 | TMP-009 | Deployed dev Job; operational readiness decisions | Controlled dev operating procedure
TMP-024 | TMP-EP07 | Create support runbook, alerting, and handover | Prepare an operational handoff with actionable diagnosis and escalation. | Define monitoring on Job/audit/reject/break signals; alerting and support ownership are not implemented in the repo. | Runbook describes failed task diagnosis, source repair, safe rerun, reconciliation, and escalation owner.; Alert criteria and response targets are approved and tested; proposed five-minute detection target remains proposed until measured.; Handover includes architecture, data contracts, access, known limitations, deployment procedure, and open risks. | 3 | High | PLANNED | Sprint 4 | BR-007; BR-008 | FR-011; FR-012; FR-013 | TMP-003; TMP-019; TMP-022; TMP-023 | Approved NFRs; report; reconciliation; support contacts | Runbook, notification path, handover sign-off

## Subtasks
Subtask ID | Parent story | Description | Expected output | Dependency
TMP-001-ST01 | TMP-001 | Inventory code, DDL, tests, docs, and deployment assets | Completed evidence for inventory code, ddl, tests, docs, and deployment assets | Parent story and its predecessors
TMP-001-ST02 | TMP-001 | Review prototype boundaries and obtain scope decisions | Completed evidence for review prototype boundaries and obtain scope decisions | Parent story and its predecessors
TMP-002-ST01 | TMP-002 | Interview trading, operations, and technology stakeholders | Completed evidence for interview trading, operations, and technology stakeholders | Parent story and its predecessors
TMP-002-ST02 | TMP-002 | Review and approve BR/FR traceability and decisions | Completed evidence for review and approve br/fr traceability and decisions | Parent story and its predecessors
TMP-003-ST01 | TMP-003 | Measure demo workload and propose service thresholds | Completed evidence for measure demo workload and propose service thresholds | Parent story and its predecessors
TMP-003-ST02 | TMP-003 | Confirm security, retention, recovery, and support policies | Completed evidence for confirm security, retention, recovery, and support policies | Parent story and its predecessors
TMP-004-ST01 | TMP-004 | Trace workflow and component ownership from code/config | Completed evidence for trace workflow and component ownership from code/config | Parent story and its predecessors
TMP-004-ST02 | TMP-004 | Review target-state gap and architecture decisions | Completed evidence for review target-state gap and architecture decisions | Parent story and its predecessors
TMP-005-ST01 | TMP-005 | Confirm target workspaces, principals, and data access | Completed evidence for confirm target workspaces, principals, and data access | Parent story and its predecessors
TMP-005-ST02 | TMP-005 | Document secret, grant, and deployment configuration controls | Completed evidence for document secret, grant, and deployment configuration controls | Parent story and its predecessors
TMP-006-ST01 | TMP-006 | Confirm 14-column schema and required fields | Completed evidence for confirm 14-column schema and required fields | Parent story and its predecessors
TMP-006-ST02 | TMP-006 | Agree source snapshot, correction, cancellation, and replay rules | Completed evidence for agree source snapshot, correction, cancellation, and replay rules | Parent story and its predecessors
TMP-007-ST01 | TMP-007 | Assess provider options, licensing, and connection method | Completed evidence for assess provider options, licensing, and connection method | Parent story and its predecessors
TMP-007-ST02 | TMP-007 | Approve close definition, currency, corrections, and session coverage | Completed evidence for approve close definition, currency, corrections, and session coverage | Parent story and its predecessors
TMP-008-ST01 | TMP-008 | Validate table grains, keys, constraints, and lineage | Completed evidence for validate table grains, keys, constraints, and lineage | Parent story and its predecessors
TMP-008-ST02 | TMP-008 | Confirm financial types and retention/optimization choices | Completed evidence for confirm financial types and retention/optimization choices | Parent story and its predecessors
TMP-009-ST01 | TMP-009 | Build wheel and validate Bundle configuration | Completed evidence for build wheel and validate bundle configuration | Parent story and its predecessors
TMP-009-ST02 | TMP-009 | Deploy dev bundle and capture run evidence | Completed evidence for deploy dev bundle and capture run evidence | Parent story and its predecessors
TMP-010-ST01 | TMP-010 | Add package/test/Bundle validation pipeline | Completed evidence for add package/test/bundle validation pipeline | Parent story and its predecessors
TMP-010-ST02 | TMP-010 | Define artifact promotion, approvals, and rollback evidence | Completed evidence for define artifact promotion, approvals, and rollback evidence | Parent story and its predecessors
TMP-011-ST01 | TMP-011 | Validate file schema and structural integrity | Completed evidence for validate file schema and structural integrity | Parent story and its predecessors
TMP-011-ST02 | TMP-011 | Write and audit distinct full-snapshot Bronze rows | Completed evidence for write and audit distinct full-snapshot bronze rows | Parent story and its predecessors
TMP-012-ST01 | TMP-012 | Select append-only event or snapshot reconciliation approach | Completed evidence for select append-only event or snapshot reconciliation approach | Parent story and its predecessors
TMP-012-ST02 | TMP-012 | Implement and test disappearance/cancellation/correction cases | Completed evidence for implement and test disappearance/cancellation/correction cases | Parent story and its predecessors
TMP-013-ST01 | TMP-013 | Normalize daily provider payload and date range | Completed evidence for normalize daily provider payload and date range | Parent story and its predecessors
TMP-013-ST02 | TMP-013 | Merge price history and audit source outcomes | Completed evidence for merge price history and audit source outcomes | Parent story and its predecessors
TMP-014-ST01 | TMP-014 | Define deterministic test source and provider configuration | Completed evidence for define deterministic test source and provider configuration | Parent story and its predecessors
TMP-014-ST02 | TMP-014 | Document missing-price triage, correction, and retry behavior | Completed evidence for document missing-price triage, correction, and retry behavior | Parent story and its predecessors
TMP-015-ST01 | TMP-015 | Cast and validate typed trade/price values | Completed evidence for cast and validate typed trade/price values | Parent story and its predecessors
TMP-015-ST02 | TMP-015 | Apply dedupe/version rules and idempotent reject MERGE | Completed evidence for apply dedupe/version rules and idempotent reject merge | Parent story and its predecessors
TMP-016-ST01 | TMP-016 | Execute Spark/Delta tests in a provisioned environment | Completed evidence for execute spark/delta tests in a provisioned environment | Parent story and its predecessors
TMP-016-ST02 | TMP-016 | Run same-input job twice and compare business outputs | Completed evidence for run same-input job twice and compare business outputs | Parent story and its predecessors
TMP-017-ST01 | TMP-017 | Aggregate daily flows and cumulative positions | Completed evidence for aggregate daily flows and cumulative positions | Parent story and its predecessors
TMP-017-ST02 | TMP-017 | Value at exact-date close and reconcile history | Completed evidence for value at exact-date close and reconcile history | Parent story and its predecessors
TMP-018-ST01 | TMP-018 | Calculate opening inventory price move and trade-day term | Completed evidence for calculate opening inventory price move and trade-day term | Parent story and its predecessors
TMP-018-ST02 | TMP-018 | Reconcile output and label simplified P&L limitations | Completed evidence for reconcile output and label simplified p&l limitations | Parent story and its predecessors
TMP-019-ST01 | TMP-019 | Trigger and monitor controlled Job execution | Completed evidence for trigger and monitor controlled job execution | Parent story and its predecessors
TMP-019-ST02 | TMP-019 | Report audit, rejects, Gold outcomes, and unavailable metrics | Completed evidence for report audit, rejects, gold outcomes, and unavailable metrics | Parent story and its predecessors
TMP-020-ST01 | TMP-020 | Agree dashboard user journeys and query model | Completed evidence for agree dashboard user journeys and query model | Parent story and its predecessors
TMP-020-ST02 | TMP-020 | Build, permission, and reconcile dashboard views | Completed evidence for build, permission, and reconcile dashboard views | Parent story and its predecessors
TMP-021-ST01 | TMP-021 | Run and triage current unit/static test suite | Completed evidence for run and triage current unit/static test suite | Parent story and its predecessors
TMP-021-ST02 | TMP-021 | Update stale DDL test paths and maintain focused rule tests | Completed evidence for update stale ddl test paths and maintain focused rule tests | Parent story and its predecessors
TMP-022-ST01 | TMP-022 | Re-run independent position and P&L reconciliation | Completed evidence for re-run independent position and p&l reconciliation | Parent story and its predecessors
TMP-022-ST02 | TMP-022 | Obtain business acceptance and capture rerun evidence | Completed evidence for obtain business acceptance and capture rerun evidence | Parent story and its predecessors
TMP-023-ST01 | TMP-023 | Verify run parameters, concurrency, retries, and task dependencies | Completed evidence for verify run parameters, concurrency, retries, and task dependencies | Parent story and its predecessors
TMP-023-ST02 | TMP-023 | Document schedule gate and manual recovery controls | Completed evidence for document schedule gate and manual recovery controls | Parent story and its predecessors
TMP-024-ST01 | TMP-024 | Define alert rules, support rota, and escalation process | Completed evidence for define alert rules, support rota, and escalation process | Parent story and its predecessors
TMP-024-ST02 | TMP-024 | Write recovery/runbook and conduct handover walkthrough | Completed evidence for write recovery/runbook and conduct handover walkthrough | Parent story and its predecessors

## Acceptance Criteria
Story ID | Story title | AC # | Testable acceptance criterion
TMP-001 | Baseline current implementation and confirm scope | 1 | Inventory covers all six workflow tasks, 10 physical tables, two notebooks, Bundle targets, and test evidence.
TMP-001 | Baseline current implementation and confirm scope | 2 | Every capability is labelled implemented, partial, planned, or to be confirmed with a repository evidence reference.
TMP-001 | Baseline current implementation and confirm scope | 3 | Business owner confirms prototype scope and named decision owners before Sprint 2 exit.
TMP-002 | Approve business and functional requirements | 1 | All eight business requirements have an owner, priority, acceptance evidence, and dependency.
TMP-002 | Approve business and functional requirements | 2 | All 13 functional requirements identify input, processing, output, business rule, and failure behavior.
TMP-002 | Approve business and functional requirements | 3 | Product owner records decisions or explicit TBDs; no unsupported policy is silently assumed.
TMP-003 | Set measurable non-functional and operational targets | 1 | NFR-01..10 each has a confirmed target or named owner and due date for TBD.
TMP-003 | Set measurable non-functional and operational targets | 2 | Performance baseline includes representative row counts, symbols, runtime, and cost.
TMP-003 | Set measurable non-functional and operational targets | 3 | Retention, access classification, RTO/RPO, support hours, and alert response are approved or explicitly excluded from prototype.
TMP-004 | Document and validate existing solution architecture | 1 | Current architecture matches databricks.yml, job YAML, source modules, and DDL.
TMP-004 | Document and validate existing solution architecture | 2 | Trade/price parallel branches and join dependencies are accurate.
TMP-004 | Document and validate existing solution architecture | 3 | Current provider, paused schedule, dev-only target, and notebook reporting are labelled as implemented/current limitations.
TMP-005 | Approve target security and environment architecture | 1 | Environment promotion and job identity are approved by platform owner.
TMP-005 | Approve target security and environment architecture | 2 | Unity Catalog grants cover required schemas and Volume only; no secrets are committed.
TMP-005 | Approve target security and environment architecture | 3 | Architecture labels all unprovisioned targets and controls as proposed.
TMP-006 | Confirm trade source contract and snapshot semantics | 1 | Trade source owner, file schema, delivery cutoff, completeness marker, and correction/deletion semantics are recorded.
TMP-006 | Confirm trade source contract and snapshot semantics | 2 | A missing trade in a later snapshot is not treated as a cancellation without explicit business rule.
TMP-006 | Confirm trade source contract and snapshot semantics | 3 | Sample volume, retention, privacy classification, and replay window are approved or tracked as TBD.
TMP-007 | Select and approve market-data source | 1 | Provider and business owner approve data rights and use case before production.
TMP-007 | Select and approve market-data source | 2 | Price-date/price-type/currency contract and correction policy are documented.
TMP-007 | Select and approve market-data source | 3 | Daily availability and expected-session completeness thresholds have named owners.
TMP-008 | Approve physical data dictionary and retention model | 1 | Data dictionary lists every column and exact DDL type/nullability for all 10 tables.
TMP-008 | Approve physical data dictionary and retention model | 2 | Business owner approves table grain and logical key assumptions.
TMP-008 | Approve physical data dictionary and retention model | 3 | Partitioning/clustering remains absent unless measured query patterns justify it.
TMP-008 | Approve physical data dictionary and retention model | 4 | Retention and Delta cleanup policy are approved before any production purge/optimization.
TMP-009 | Maintain reproducible Databricks Asset Bundle development deployment | 1 | Bundle validation succeeds with the documented dev target and CLI profile.
TMP-009 | Maintain reproducible Databricks Asset Bundle development deployment | 2 | Wheel contains all six entry points and deploy uses repository source.
TMP-009 | Maintain reproducible Databricks Asset Bundle development deployment | 3 | Manual smoke run evidence is attached; no production readiness is inferred.
TMP-010 | Add reviewed CI checks and controlled deployment promotion | 1 | Pull request CI runs deterministic local tests and Bundle validation without credentials in logs.
TMP-010 | Add reviewed CI checks and controlled deployment promotion | 2 | Deployment artifact/version is traceable to reviewed source revision.
TMP-010 | Add reviewed CI checks and controlled deployment promotion | 3 | Promotion cannot unpause a schedule or deploy to an unapproved target without explicit approval.
TMP-011 | Ingest synthetic trade snapshot into Bronze | 1 | Exact schema, empty-file, and malformed-row cases are tested.
TMP-011 | Ingest synthetic trade snapshot into Bronze | 2 | Identical in-batch records are removed; versions of a trade remain present.
TMP-011 | Ingest synthetic trade snapshot into Bronze | 3 | Invalid file never overwrites existing Bronze; valid rerun yields same business rows.
TMP-012 | Resolve trade snapshot disappearance and historical correction controls | 1 | Trade owner approves semantics for missing trade IDs, cancellation, and correction.
TMP-012 | Resolve trade snapshot disappearance and historical correction controls | 2 | A two-snapshot test proves accepted Silver matches the agreed authoritative source state.
TMP-012 | Resolve trade snapshot disappearance and historical correction controls | 3 | Backdated corrections are traceable and recompute the intended history without unrelated deletes.
TMP-013 | Ingest and retain daily market-price history | 1 | Default symbols, date boundaries, provider response variants, NaN, duplicate keys, and retry errors have deterministic tests.
TMP-013 | Ingest and retain daily market-price history | 2 | Price rows carry source, currency, ingestion timestamp, and run lineage.
TMP-013 | Ingest and retain daily market-price history | 3 | Provider limitations and data rights are explicit in the source contract.
TMP-014 | Harden price source decision and completeness exception process | 1 | Missing expected session is tied to symbol/date and owner; no stale price is used for position valuation.
TMP-014 | Harden price source decision and completeness exception process | 2 | Test fixtures are deterministic and cannot be mistaken for production source data.
TMP-014 | Harden price source decision and completeness exception process | 3 | Approved provider/credentials, rate limits, correction policy, and retries are configured outside source code where required.
TMP-015 | Validate Silver trades and prices with reject history | 1 | Trade and price fixtures cover configured rules and reason codes.
TMP-015 | Validate Silver trades and prices with reject history | 2 | Silver trade business key is trade_id; price key is symbol + price_date.
TMP-015 | Validate Silver trades and prices with reject history | 3 | Reject writes are idempotent and preserve raw source fields/lineage; missing expected price blocks Silver update.
TMP-016 | Run Spark/Delta integration and end-to-end rerun validation | 1 | Spark/Delta integration suite runs in a supported CI or Databricks test environment and results are retained.
TMP-016 | Run Spark/Delta integration and end-to-end rerun validation | 2 | A second complete run with the same inputs verifies stable business keys/values and expected audit history growth.
TMP-016 | Run Spark/Delta integration and end-to-end rerun validation | 3 | Failure injection confirms no unsafe publication and a documented rerun recovers the task.
TMP-017 | Build cumulative daily positions and exact-date valuation | 1 | Position grain and key match the approved dictionary.
TMP-017 | Build cumulative daily positions and exact-date valuation | 2 | Daily buys, sells, net, closing quantity, close, and market value reconcile to independent calculations.
TMP-017 | Build cumulative daily positions and exact-date valuation | 3 | Missing same-day price leaves price/value NULL and creates a break without changing quantity.
TMP-018 | Calculate daily cash-equity mark-to-market P&L | 1 | Daily output grain is valuation_date + book_id + symbol + currency.
TMP-018 | Calculate daily cash-equity mark-to-market P&L | 2 | Price movement and trade-day terms reconcile independently, including sells, new/flat positions, prior-close baseline, and missing prices.
TMP-018 | Calculate daily cash-equity mark-to-market P&L | 3 | unrealized_pnl_proxy is clearly labelled as a cumulative proxy and is not presented as true unrealized P&L.
TMP-019 | Provide notebook and SQL operational reporting | 1 | Run report identifies audit-derived status and clearly marks unavailable counts.
TMP-019 | Provide notebook and SQL operational reporting | 2 | Notebook output is read-only and totals reconcile to source tables.
TMP-019 | Provide notebook and SQL operational reporting | 3 | Report states that scheduled-run completeness is not evaluated and dashboard is not implemented.
TMP-020 | Deliver user-accepted trading and P&L dashboard MVP | 1 | Product owner signs off audience, filters, date/book/symbol dimensions, and exception drill-through.
TMP-020 | Deliver user-accepted trading and P&L dashboard MVP | 2 | Dashboard totals reconcile to Gold daily_pnl and positions for agreed test dates.
TMP-020 | Deliver user-accepted trading and P&L dashboard MVP | 3 | Dashboard access is least privilege and deployment is repeatable; no dashboard is reported as live before sign-off.
TMP-021 | Maintain deterministic unit and transformation tests | 1 | Business-rule tests include correction, duplicate, calendar, missing price, short position, and P&L decomposition cases.
TMP-021 | Maintain deterministic unit and transformation tests | 2 | CI reports skips separately from passes and does not treat unavailable Spark tests as verified.
TMP-021 | Maintain deterministic unit and transformation tests | 3 | Replace stale test references with the consolidated Silver DDL and verify its CHECK constraints.
TMP-021 | Maintain deterministic unit and transformation tests | 4 | New failures are triaged against the baseline; no unrelated failures are silently waived.
TMP-022 | Complete independent position/P&L reconciliation and UAT | 1 | Trade-to-position quantities reconcile by date/book/counterparty/instrument.
TMP-022 | Complete independent position/P&L reconciliation and UAT | 2 | Position market value and daily P&L reconcile using approved close/baseline/trade cash-flow methodology.
TMP-022 | Complete independent position/P&L reconciliation and UAT | 3 | Business owner signs UAT evidence for representative long, short, flat, correction, and missing-price cases.
TMP-022 | Complete independent position/P&L reconciliation and UAT | 4 | A complete same-input rerun has recorded evidence; do not rely only on unit tests.
TMP-023 | Operate the dev workflow with controlled scheduling | 1 | Manual run and failure states are visible in Job UI and audit tables.
TMP-023 | Operate the dev workflow with controlled scheduling | 2 | Schedule remains paused until source owner, support contact, permissions, runbook, and alert path are approved.
TMP-023 | Operate the dev workflow with controlled scheduling | 3 | Any future unpause/change is reviewed and recorded with owner and rollback path.
TMP-024 | Create support runbook, alerting, and handover | 1 | Runbook describes failed task diagnosis, source repair, safe rerun, reconciliation, and escalation owner.
TMP-024 | Create support runbook, alerting, and handover | 2 | Alert criteria and response targets are approved and tested; proposed five-minute detection target remains proposed until measured.
TMP-024 | Create support runbook, alerting, and handover | 3 | Handover includes architecture, data contracts, access, known limitations, deployment procedure, and open risks.

## Dependencies
Predecessor | Successor | Relationship | Dependency type | Sprint/status | Rationale / expected output
TMP-001 | TMP-002 | blocks | Story delivery dependency | Sprint 1 | Predecessor output required before dependent story acceptance
TMP-002 | TMP-003 | blocks | Story delivery dependency | Sprint 1 | Predecessor output required before dependent story acceptance
TMP-002 | TMP-005 | blocks | Story delivery dependency | Sprint 2 | Predecessor output required before dependent story acceptance
TMP-003 | TMP-005 | blocks | Story delivery dependency | Sprint 2 | Predecessor output required before dependent story acceptance
TMP-004 | TMP-005 | blocks | Story delivery dependency | Sprint 2 | Predecessor output required before dependent story acceptance
TMP-002 | TMP-007 | blocks | Story delivery dependency | Sprint 2 | Predecessor output required before dependent story acceptance
TMP-006 | TMP-008 | blocks | Story delivery dependency | Sprint 5 | Predecessor output required before dependent story acceptance
TMP-007 | TMP-008 | blocks | Story delivery dependency | Sprint 5 | Predecessor output required before dependent story acceptance
TMP-005 | TMP-010 | blocks | Story delivery dependency | Sprint 3 | Predecessor output required before dependent story acceptance
TMP-009 | TMP-010 | blocks | Story delivery dependency | Sprint 3 | Predecessor output required before dependent story acceptance
TMP-006 | TMP-011 | blocks | Story delivery dependency | Current/complete | Predecessor output required before dependent story acceptance
TMP-006 | TMP-012 | blocks | Story delivery dependency | Sprint 3 | Predecessor output required before dependent story acceptance
TMP-011 | TMP-012 | blocks | Story delivery dependency | Sprint 3 | Predecessor output required before dependent story acceptance
TMP-007 | TMP-013 | blocks | Story delivery dependency | Current/complete | Predecessor output required before dependent story acceptance
TMP-007 | TMP-014 | blocks | Story delivery dependency | Sprint 5 | Predecessor output required before dependent story acceptance
TMP-013 | TMP-014 | blocks | Story delivery dependency | Sprint 5 | Predecessor output required before dependent story acceptance
TMP-011 | TMP-015 | blocks | Story delivery dependency | Current/complete | Predecessor output required before dependent story acceptance
TMP-013 | TMP-015 | blocks | Story delivery dependency | Current/complete | Predecessor output required before dependent story acceptance
TMP-015 | TMP-016 | blocks | Story delivery dependency | Sprint 4 | Predecessor output required before dependent story acceptance
TMP-015 | TMP-017 | blocks | Story delivery dependency | Current/complete | Predecessor output required before dependent story acceptance
TMP-017 | TMP-018 | blocks | Story delivery dependency | Current/complete | Predecessor output required before dependent story acceptance
TMP-018 | TMP-019 | blocks | Story delivery dependency | Current/complete | Predecessor output required before dependent story acceptance
TMP-002 | TMP-020 | blocks | Story delivery dependency | Sprint 5 | Predecessor output required before dependent story acceptance
TMP-008 | TMP-020 | blocks | Story delivery dependency | Sprint 5 | Predecessor output required before dependent story acceptance
TMP-018 | TMP-020 | blocks | Story delivery dependency | Sprint 5 | Predecessor output required before dependent story acceptance
TMP-019 | TMP-020 | blocks | Story delivery dependency | Sprint 5 | Predecessor output required before dependent story acceptance
TMP-016 | TMP-022 | blocks | Story delivery dependency | Sprint 4 | Predecessor output required before dependent story acceptance
TMP-018 | TMP-022 | blocks | Story delivery dependency | Sprint 4 | Predecessor output required before dependent story acceptance
TMP-009 | TMP-023 | blocks | Story delivery dependency | Sprint 2 | Predecessor output required before dependent story acceptance
TMP-003 | TMP-024 | blocks | Story delivery dependency | Sprint 4 | Predecessor output required before dependent story acceptance
TMP-019 | TMP-024 | blocks | Story delivery dependency | Sprint 4 | Predecessor output required before dependent story acceptance
TMP-022 | TMP-024 | blocks | Story delivery dependency | Sprint 4 | Predecessor output required before dependent story acceptance
TMP-023 | TMP-024 | blocks | Story delivery dependency | Sprint 4 | Predecessor output required before dependent story acceptance
ingest_prices | process_prices | blocks | Implemented Databricks Workflow dependency | Current workflow | Verified in jobs/resources/trade_pipeline.job.yml
ingest_trades | process_trades | blocks | Implemented Databricks Workflow dependency | Current workflow | Verified in jobs/resources/trade_pipeline.job.yml
process_prices | build_positions | blocks | Implemented Databricks Workflow dependency | Current workflow | Verified in jobs/resources/trade_pipeline.job.yml
process_trades | build_positions | blocks | Implemented Databricks Workflow dependency | Current workflow | Verified in jobs/resources/trade_pipeline.job.yml
build_positions | calculate_daily_pnl | blocks | Implemented Databricks Workflow dependency | Current workflow | Verified in jobs/resources/trade_pipeline.job.yml

## Sprints
Sprint | Timeline | Plan classification | Sprint goal | Planned stories | Capacity (SP) | Planned SP (formula) | Headroom / (over) (formula) | Dependencies | Deliverables | Demonstration | Exit criteria
Sprint 1 | Weeks 1-2 | 8-week baseline | Baseline scope, requirements, NFRs, and trade source semantics; identify decision owners. | TMP-001; TMP-002; TMP-003; TMP-006 | 10 |  |  | Kickoff; timely access to product, trading operations, and trade-source decision owners. | Implementation baseline, BR/FR and NFR decisions, trade source contract and correction semantics. | Walk from 14-column synthetic CSV contract to Bronze/Silver rules and show acceptance traceability. | No critical requirement or source decision is ownerless; trade snapshot/correction semantics recorded.
Sprint 2 | Weeks 3-4 | 8-week baseline | Close target access design, market-data decision, and controlled dev operating procedure. | TMP-005; TMP-007; TMP-023 | 10 |  |  | Sprint 1 requirements; platform/security and market-data decision owners. | Environment/access design, market-data decision or prototype-only boundary, workflow/schedule gate. | Review source-provider decision criteria, Bundle target, permissions, and paused schedule gate. | No production source or target is represented as approved without evidence.
Sprint 3 | Weeks 5-6 | 8-week baseline | Establish reviewed CI/deployment controls and resolve trade snapshot correction behavior. | TMP-010; TMP-012 | 10 |  |  | Approved environment design and trade-source semantics from Sprint 1/2. | CI and promotion checks; two-snapshot correction/disappearance behavior and test evidence. | Show PR checks and a source correction/deletion scenario through position history. | A source correction has an explicit rule and a test; deployment promotion remains gated.
Sprint 4 | Weeks 7-8 | 8-week baseline | Close test failures, supported-runtime rerun/reconciliation, and operational handover. | TMP-016; TMP-021; TMP-022; TMP-024 | 10 |  |  | Supported Spark/Delta runtime, source decisions, test access, and support role participation. | Fixed stale DDL test references, integration/idempotency evidence, UAT reconciliation, runbook and handover. | Show a rerun comparison, financial reconciliation, and failure-to-recovery walkthrough. | Known critical defects closed or explicitly accepted; production schedule remains paused without a separate go-live gate.
Sprint 5 (Optional) | Weeks 9-10 (follow-on; not in 8-week baseline) | Optional follow-on | Complete follow-on data approval, missing-price operations, dictionary approval, and dashboard MVP if authorized. | TMP-008; TMP-014; TMP-020 | 10 |  |  | Confirmed reporting audience, approved source, retained capacity, and business sign-off. | Approved data dictionary/retention decisions, price exception procedure, dashboard MVP and reconciliation. | Demonstrate a role-controlled dashboard and missing-price drill-through reconciled to Gold. | Follow-on scope is approved and dashboard totals/access are accepted; no assumed production go-live.

## Gantt
Activity ID | Workstream / task | Jira story IDs | Duration basis | Start week | Finish week | Predecessor activity / story IDs | Milestone | Implementation evidence status | Schedule status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
WS-01 | Requirements and scope | TMP-001; TMP-002; TMP-003 | Two-week sprint allocation window; task-level duration is not specified | 1 | 2 | None | M-01 | PARTIALLY IMPLEMENTED | PLANNED
WS-02 | Trade source contract | TMP-006 | Two-week sprint allocation window; task-level duration is not specified | 1 | 2 | None | M-01 | PARTIALLY IMPLEMENTED | PLANNED
WS-03 | Security and environment design | TMP-005 | Two-week sprint allocation window; task-level duration is not specified | 3 | 4 | WS-01; TMP-004 | M-02 | PLANNED | PLANNED
WS-04 | Market-data provider decision | TMP-007 | Two-week sprint allocation window; task-level duration is not specified | 3 | 4 | WS-01 | M-02 | PLANNED | PLANNED
WS-05 | Workflow and schedule gate | TMP-023 | Two-week sprint allocation window; task-level duration is not specified | 3 | 4 | TMP-009 | M-02 | PARTIALLY IMPLEMENTED | PLANNED
WS-06 | CI/CD promotion controls | TMP-010 | Two-week sprint allocation window; task-level duration is not specified | 5 | 6 | WS-03; TMP-009 | M-03 | PLANNED | PLANNED
WS-07 | Trade correction and history | TMP-012 | Two-week sprint allocation window; task-level duration is not specified | 5 | 6 | WS-02; TMP-011 | M-03 | PLANNED | PLANNED
WS-08 | Spark/Delta rerun validation | TMP-016 | Two-week sprint allocation window; task-level duration is not specified | 7 | 8 | TMP-015 | M-04 | PLANNED | PLANNED
WS-09 | Test maintenance and QA | TMP-021 | Two-week sprint allocation window; task-level duration is not specified | 7 | 8 | None | M-04 | PARTIALLY IMPLEMENTED | PLANNED
WS-10 | Reconciliation and UAT | TMP-022 | Two-week sprint allocation window; task-level duration is not specified | 7 | 8 | WS-08; TMP-018 | M-04 | PARTIALLY IMPLEMENTED | PLANNED
WS-11 | Operations handover | TMP-024 | Two-week sprint allocation window; task-level duration is not specified | 7 | 8 | WS-01; WS-05; WS-10; TMP-019 | M-04 | PLANNED | PLANNED
| Milestone markers |  | Week-end gates | [6 empty] | Week 2: M-01; Week 4: M-02; Week 6: M-03; Week 8: M-04
Scheduling note | Bars show assigned two-week sprint windows only; they are not task-level durations. No kickoff date, activity duration, resource-levelled calendar, CPM dates, or float is evidenced. Sprint 5 (Weeks 9-10) is optional follow-on and is not plotted.

## Milestone Tracker
Milestone ID | Milestone | Planned date/week | Exit evidence | Accountable owner | Dependencies | Approval requirements | Exit criteria | Status
M-01 | Scope, requirements and trade contract baseline | End Week 2 | Approved BR/FR/NFR decisions; trade source/version/correction semantics; named decision owners | Technical Project Manager / Product Owner | TMP-001; TMP-002; TMP-003; TMP-006 | Product Owner and Trade Data Owner; role names proposed, identities TBD | Business/product approval; no unowned critical assumption | PLANNED
M-02 | Source and access design gate | End Week 4 | Market-data source decision; target identity/access design; dev workflow gate | Solution Architect / Market Data Owner | TMP-005; TMP-007; TMP-023 | Platform/Security and Market Data Owner; no production access approval assumed | Provider approval or explicit prototype-only boundary; security review of design | PLANNED
M-03 | Engineering controls and trade-history gate | End Week 6 | CI evidence; trade correction/disappearance test; deployment control review | Lead Data Engineer / Technical Project Manager | TMP-010; TMP-012 | Engineering owner and Product Control review of affected trade semantics | PR checks and correction behavior pass agreed acceptance criteria | PLANNED
M-04 | Prototype acceptance and handover | End Week 8 | Supported-runtime tests; same-input rerun; reconciliation/UAT; runbook and support walkthrough | Product Control / Production Support | TMP-016; TMP-021; TMP-022; TMP-024 | Product Control, QA, Production Support, and Sponsor go/no-go for prototype exit | Business acceptance and operational readiness review; schedule remains paused absent separate approval | PLANNED
M-05 | Optional dashboard and data sign-off | End Week 10 (optional follow-on) | Approved reporting/data decisions; dashboard reconciliation and role access | Product Owner / Product Control | TMP-008; TMP-014; TMP-020 | Product Owner, Product Control, and access owner | Dashboard acceptance and business data approval; not a production release approval | PLANNED

## RAID
ID | Type | Description | Probability | Impact | Owner | Mitigation / action | Due date/week | Trigger | Escalation path | Status
R-01 | Risk | Yahoo Finance is not established as an approved or licensed institutional market-data source. | High | High | Market Data Owner | Obtain provider/data-rights decision in Sprint 2; keep production scope blocked until approved source is selected. | End Week 4 gate | No approved provider/rights or completeness owner by source gate. | Market Data Owner → Sponsor; Security/Legal/Data Governance as applicable. | Open
R-02 | Risk | Full-snapshot trade Bronze can leave stale Silver trades when trade IDs disappear from later files. | Medium | High | Trade Data Owner | Agree cancellation/deletion semantics and implement two-snapshot reconciliation test before relying on external trade feed. | End Week 6 gate | A two-snapshot comparison leaves a trade in Silver after authoritative removal/correction. | Trading Operations and Product Control → Sponsor if semantics affect positions/P&L. | Open
R-03 | Risk | Full-history recomputation and free-form instrument/book data may not scale or satisfy control expectations. | Medium | High | Lead Data Engineer | Benchmark representative scale; establish reference ownership and incremental strategy from evidence. | Before any production scale decision | Representative-volume benchmark exceeds proposed runtime/cost or reference mapping is inconsistent. | Lead Engineer / Architect → TPM → Sponsor for scope/capacity decision. | Open
R-04 | Risk | Eight-week plan has no capacity reserve and depends on part-time approvers and test runtime access. | Medium | High | Project Manager | Reserve decision owners at Sprint start; defer dashboard polish or extend by one sprint if critical access/decisions slip. | Weekly; reforecast each sprint | Decision/access delay consumes the 2-point baseline headroom or threatens a gate. | TPM → Sponsor; defer optional dashboard/follow-on or approve added capacity. | Open
A-01 | Assumption | Initial scope remains USD cash equities, 10 configured instruments, and one development workspace. | N/A | High | Product Owner | Product owner confirms before Sprint 1 exit; FX, derivatives, fees, and corporate actions stay out of scope. | End Week 2 | Request includes FX, derivatives, fees, corporate actions, or additional instruments. | BA/PO and Product Control → Sponsor through change control. | To confirm
I-01 | Issue | A documented second same-parameter Databricks run was queued and has no recorded outcome. | N/A | Medium | QA / Lead Engineer | Run and compare business keys/values in a supported runtime; retain evidence. | Sprint 4 exit | Same-input Job run evidence remains absent. | QA / Lead Engineer → TPM; hold idempotency acceptance. | Open
I-02 | Issue | Three focused local tests fail because they read removed Silver *_constraints.sql files; the checks now reside in consolidated trades.sql and market_prices.sql. | N/A | Medium | Lead Engineer / QA | Update stale test paths and assertions to the consolidated DDL, then rerun focused and full suite; application/test changes are outside this documentation task. | Sprint 4 exit | Tests still reference removed constraint scripts or focused failures persist. | QA / Lead Engineer → TPM; hold quality gate or document approved exception. | Open
D-01 | Dependency | Production environment, service principal, data rights, source owners, and reporting audience are not evidenced. | High | High | Project Manager | Record named decision owner and due date; keep job schedule paused until readiness gate. | End Week 2 decision log; before any non-dev release | No owner, target identity, data-rights decision, or test runtime is available. | TPM → Sponsor and accountable platform/data/security owner; release blocked. | Open
A-02 | Assumption | Two-week sprint estimates use 10 story points of lead-engineer delivery capacity per sprint, with part-time BA/architect/QA support. | N/A | Medium | Project Manager | Re-estimate at planning; the eight-week baseline has no reserve and is not a committed calendar date. | Each sprint planning | Committed role capacity or actual throughput differs from assumption. | TPM reforecasts with Sponsor; protect quality, reduce scope, or add approved time/capacity. | Proposed

## Traceability
Business requirement | Functional requirement | Jira story | Test case(s) | Acceptance evidence | Implementation status
BR-001 | FR-001 | TMP-011 | TC-001 | tests/test_ingest_trades.py; capture supported-runtime run | IMPLEMENTED
BR-001 | FR-003 | TMP-015 | TC-003 | tests/test_trades.py; tests/test_process_prices.py | IMPLEMENTED
BR-001 | FR-003 | TMP-016 | TC-003; TC-007 | tests/test_trades.py; tests/test_process_prices.py; database/tables/**/*.sql; generated Data Dictionary worksheet; update tests that still reference removed *_constraints.sql paths | PLANNED
BR-001 | FR-004 | TMP-015 | TC-003 | tests/test_trades.py; tests/test_process_prices.py | IMPLEMENTED
BR-001 | FR-004 | TMP-012 | TC-003 | tests/test_trades.py; tests/test_process_prices.py | PLANNED
BR-001 | FR-005 | TMP-015 | TC-003 | tests/test_trades.py; tests/test_process_prices.py | IMPLEMENTED
BR-001 | FR-005 | TMP-016 | TC-002; TC-003 | tests/test_ingest_prices.py; test fixtures; tests/test_trades.py; tests/test_process_prices.py | PLANNED
BR-001 | FR-013 | TMP-016 | TC-008; TC-009 | New supported Databricks/Delta run pair; compare business-key hashes; Job run URL, audit rows, recovery run and reconciliation | PLANNED
BR-001 | FR-013 | TMP-022 | TC-008 | New supported Databricks/Delta run pair; compare business-key hashes | PARTIALLY IMPLEMENTED
BR-001 | FR-013 | TMP-024 | TC-009; TC-012 | Job run URL, audit rows, recovery run and reconciliation; Access review, CI/deploy log, alert test, runbook walkthrough | PLANNED
BR-002 | FR-002 | TMP-013 | TC-002 | tests/test_ingest_prices.py; test fixtures | IMPLEMENTED
BR-002 | FR-002 | TMP-014 | TC-002 | tests/test_ingest_prices.py; test fixtures | PLANNED
BR-002 | FR-003 | TMP-015 | TC-003 | tests/test_trades.py; tests/test_process_prices.py | IMPLEMENTED
BR-002 | FR-003 | TMP-016 | TC-003; TC-007 | tests/test_trades.py; tests/test_process_prices.py; database/tables/**/*.sql; generated Data Dictionary worksheet; update tests that still reference removed *_constraints.sql paths | PLANNED
BR-002 | FR-005 | TMP-015 | TC-003 | tests/test_trades.py; tests/test_process_prices.py | IMPLEMENTED
BR-002 | FR-005 | TMP-016 | TC-002; TC-003 | tests/test_ingest_prices.py; test fixtures; tests/test_trades.py; tests/test_process_prices.py | PLANNED
BR-002 | FR-013 | TMP-016 | TC-008; TC-009 | New supported Databricks/Delta run pair; compare business-key hashes; Job run URL, audit rows, recovery run and reconciliation | PLANNED
BR-002 | FR-013 | TMP-022 | TC-008 | New supported Databricks/Delta run pair; compare business-key hashes | PARTIALLY IMPLEMENTED
BR-002 | FR-013 | TMP-024 | TC-009; TC-012 | Job run URL, audit rows, recovery run and reconciliation; Access review, CI/deploy log, alert test, runbook walkthrough | PLANNED
BR-003 | FR-004 | TMP-015 | TC-003 | tests/test_trades.py; tests/test_process_prices.py | IMPLEMENTED
BR-003 | FR-004 | TMP-012 | TC-003 | tests/test_trades.py; tests/test_process_prices.py | PLANNED
BR-003 | FR-005 | TMP-015 | TC-003 | tests/test_trades.py; tests/test_process_prices.py | IMPLEMENTED
BR-003 | FR-005 | TMP-016 | TC-002; TC-003 | tests/test_ingest_prices.py; test fixtures; tests/test_trades.py; tests/test_process_prices.py | PLANNED
BR-003 | FR-009 | TMP-012 | TC-004; TC-008 | tests/test_build_positions.py; independent SQL reconciliation; New supported Databricks/Delta run pair; compare business-key hashes | PLANNED
BR-003 | FR-009 | TMP-017 | TC-004 | tests/test_build_positions.py; independent SQL reconciliation | IMPLEMENTED
BR-003 | FR-009 | TMP-018 | TC-004; TC-008 | tests/test_build_positions.py; independent SQL reconciliation; New supported Databricks/Delta run pair; compare business-key hashes | IMPLEMENTED
BR-003 | FR-013 | TMP-016 | TC-008; TC-009 | New supported Databricks/Delta run pair; compare business-key hashes; Job run URL, audit rows, recovery run and reconciliation | PLANNED
BR-003 | FR-013 | TMP-022 | TC-008 | New supported Databricks/Delta run pair; compare business-key hashes | PARTIALLY IMPLEMENTED
BR-003 | FR-013 | TMP-024 | TC-009; TC-012 | Job run URL, audit rows, recovery run and reconciliation; Access review, CI/deploy log, alert test, runbook walkthrough | PLANNED
BR-004 | FR-006 | TMP-017 | TC-004 | tests/test_build_positions.py; independent SQL reconciliation | IMPLEMENTED
BR-004 | FR-007 | TMP-017 | TC-005 | tests/test_build_positions.py; Gold break query | IMPLEMENTED
BR-004 | FR-009 | TMP-012 | TC-004; TC-008 | tests/test_build_positions.py; independent SQL reconciliation; New supported Databricks/Delta run pair; compare business-key hashes | PLANNED
BR-004 | FR-009 | TMP-017 | TC-004 | tests/test_build_positions.py; independent SQL reconciliation | IMPLEMENTED
BR-004 | FR-009 | TMP-018 | TC-004; TC-008 | tests/test_build_positions.py; independent SQL reconciliation; New supported Databricks/Delta run pair; compare business-key hashes | IMPLEMENTED
BR-005 | FR-007 | TMP-017 | TC-005 | tests/test_build_positions.py; Gold break query | IMPLEMENTED
BR-005 | FR-008 | TMP-018 | TC-006 | tests/test_daily_pnl.py; documented BOOK_TECH/AAPL hand check | IMPLEMENTED
BR-005 | FR-009 | TMP-012 | TC-004; TC-008 | tests/test_build_positions.py; independent SQL reconciliation; New supported Databricks/Delta run pair; compare business-key hashes | PLANNED
BR-005 | FR-009 | TMP-017 | TC-004 | tests/test_build_positions.py; independent SQL reconciliation | IMPLEMENTED
BR-005 | FR-009 | TMP-018 | TC-004; TC-008 | tests/test_build_positions.py; independent SQL reconciliation; New supported Databricks/Delta run pair; compare business-key hashes | IMPLEMENTED
BR-006 | FR-010 | TMP-019 | TC-011 | UAT scripts, screenshot/export, stakeholder sign-off | IMPLEMENTED
BR-006 | FR-010 | TMP-020 | TC-011 | UAT scripts, screenshot/export, stakeholder sign-off | BLOCKED
BR-006 | FR-011 | TMP-019 | TC-011 | UAT scripts, screenshot/export, stakeholder sign-off | IMPLEMENTED
BR-006 | FR-011 | TMP-024 | TC-009; TC-012 | Job run URL, audit rows, recovery run and reconciliation; Access review, CI/deploy log, alert test, runbook walkthrough | PLANNED
BR-007 | FR-005 | TMP-015 | TC-003 | tests/test_trades.py; tests/test_process_prices.py | IMPLEMENTED
BR-007 | FR-005 | TMP-016 | TC-002; TC-003 | tests/test_ingest_prices.py; test fixtures; tests/test_trades.py; tests/test_process_prices.py | PLANNED
BR-007 | FR-011 | TMP-019 | TC-011 | UAT scripts, screenshot/export, stakeholder sign-off | IMPLEMENTED
BR-007 | FR-011 | TMP-024 | TC-009; TC-012 | Job run URL, audit rows, recovery run and reconciliation; Access review, CI/deploy log, alert test, runbook walkthrough | PLANNED
BR-007 | FR-012 | TMP-009 | TC-010 | Bundle validate output; Job task graph and run record | IMPLEMENTED
BR-007 | FR-012 | TMP-010 | TC-010; TC-012 | Bundle validate output; Job task graph and run record; Access review, CI/deploy log, alert test, runbook walkthrough | PLANNED
BR-007 | FR-012 | TMP-023 | TC-010 | Bundle validate output; Job task graph and run record | PARTIALLY IMPLEMENTED
BR-007 | FR-013 | TMP-016 | TC-008; TC-009 | New supported Databricks/Delta run pair; compare business-key hashes; Job run URL, audit rows, recovery run and reconciliation | PLANNED
BR-007 | FR-013 | TMP-022 | TC-008 | New supported Databricks/Delta run pair; compare business-key hashes | PARTIALLY IMPLEMENTED
BR-007 | FR-013 | TMP-024 | TC-009; TC-012 | Job run URL, audit rows, recovery run and reconciliation; Access review, CI/deploy log, alert test, runbook walkthrough | PLANNED
BR-008 | FR-012 | TMP-009 | TC-010 | Bundle validate output; Job task graph and run record | IMPLEMENTED
BR-008 | FR-012 | TMP-010 | TC-010; TC-012 | Bundle validate output; Job task graph and run record; Access review, CI/deploy log, alert test, runbook walkthrough | PLANNED
BR-008 | FR-012 | TMP-023 | TC-010 | Bundle validate output; Job task graph and run record | PARTIALLY IMPLEMENTED
BR-008 | FR-013 | TMP-016 | TC-008; TC-009 | New supported Databricks/Delta run pair; compare business-key hashes; Job run URL, audit rows, recovery run and reconciliation | PLANNED
BR-008 | FR-013 | TMP-022 | TC-008 | New supported Databricks/Delta run pair; compare business-key hashes | PARTIALLY IMPLEMENTED
BR-008 | FR-013 | TMP-024 | TC-009; TC-012 | Job run URL, audit rows, recovery run and reconciliation; Access review, CI/deploy log, alert test, runbook walkthrough | PLANNED

## Test Plan
Test ID | Test level | Scope | Requirement IDs | Jira story | Expected result | Acceptance evidence | Status / note
TC-001 | Unit / file contract | Trade CSV exact header, empty/malformed file, raw strings, dedupe, no overwrite on invalid input | FR-001, FR-013 | TMP-011 | Valid file writes distinct snapshot; invalid source fails before overwrite | tests/test_ingest_trades.py; capture supported-runtime run | Planned / existing tests to rerun
TC-002 | Unit / integration | Price response normalization, retries, date window, no-price handling | FR-002, FR-005 | TMP-013, TMP-014 | Correct close records; missing expected sessions are explicit; no invented price | tests/test_ingest_prices.py; test fixtures | Planned / existing tests to rerun
TC-003 | Data quality | Silver cast, rules, reject reasons, duplicate/version precedence | FR-003, FR-004, FR-005 | TMP-015 | Valid typed rows only; deterministic rejects and one selected trade version | tests/test_trades.py; tests/test_process_prices.py | Planned / existing tests to rerun
TC-004 | Calculation / reconciliation | Daily and cumulative position, buys/sells, no-trade day, short/flat, correction | FR-006, FR-009 | TMP-017, TMP-022 | Gold quantity matches independent trade aggregation by full grain | tests/test_build_positions.py; independent SQL reconciliation | Planned / existing tests to rerun
TC-005 | Valuation | Exact-date price, currency, missing mark, null valuation and break | FR-007 | TMP-017 | Value = closing quantity * exact close; missing mark does not change quantity | tests/test_build_positions.py; Gold break query | Planned / existing tests to rerun
TC-006 | P&L reconciliation | Opening-position price move + trade-day cash-flow term; missing baseline/current close | FR-008 | TMP-018, TMP-022 | Financial values match independent Decimal calculation; missing inputs yield NULL | tests/test_daily_pnl.py; documented BOOK_TECH/AAPL hand check | Planned / existing tests to rerun
TC-007 | Schema | DDL column/type/nullability/key assumptions and financial precision | FR-003, FR-006, FR-008, FR-011 | TMP-008, TMP-021 | All 10 DDL tables appear in dictionary with exact SQL definitions | database/tables/**/*.sql; generated Data Dictionary worksheet; update tests that still reference removed *_constraints.sql paths | Planned / existing tests to rerun
TC-008 | Idempotency | Same source snapshot/date range run twice | FR-009, FR-013 | TMP-016, TMP-022 | Business values and unique keys stable; audit history reflects both attempts | New supported Databricks/Delta run pair; compare business-key hashes | Planned / existing tests to rerun
TC-009 | Recovery | Inject source/task failure and rerun after correction | FR-001, FR-011, FR-012, FR-013 | TMP-016, TMP-024 | Failure is audited, downstream blocked, corrected rerun reaches consistent outputs | Job run URL, audit rows, recovery run and reconciliation | Planned / existing tests to rerun
TC-010 | Workflow integration | Six-task DAG, parallel source branches, Bundle parameters and deployment smoke test | FR-012 | TMP-009, TMP-010, TMP-023 | Prices/trades branches run independently, join before positions, P&L runs last | Bundle validate output; Job task graph and run record | Planned / existing tests to rerun
TC-011 | Reporting / UAT | Run status, row counts, rejects, breaks, positions, P&L, dashboard access | FR-010, FR-011 | TMP-019, TMP-020, TMP-022 | Report/dashboard totals reconcile to Gold; unavailable measures are clearly labeled | UAT scripts, screenshot/export, stakeholder sign-off | Planned / existing tests to rerun
TC-012 | Deployment / operations | Environment config, least privilege, notifications, recovery, handover | FR-011, FR-012, FR-013 | TMP-005, TMP-010, TMP-024 | Approved identity and runbook are usable; schedule remains gated until readiness approval | Access review, CI/deploy log, alert test, runbook walkthrough | Planned / existing tests to rerun

## Current State
Area | Capability | Status | Verified evidence | Gap / limitation
Context | Business outcome | IMPLEMENTED (prototype scope) | Validate synthetic equity trades and daily closes, calculate daily positions/valuation/P&L, and expose exceptions. | README.md; source modules
Scope | Calculation boundary | IMPLEMENTED (simplified) | USD cash equities; ten configured instruments. Fees, FX, dividends, corporate actions, financing, borrow costs, and derivatives are excluded. | README.md; config.py; calculate_daily_pnl.py
Source | Trade input | IMPLEMENTED (synthetic) | Deterministic synthetic 14-column CSV snapshot, uploaded to Unity Catalog Volume; no upstream trading-system connector is evidenced. | scripts/generate_trades.py; bronze/ingest_trades.py
Source | Market price input | IMPLEMENTED (prototype provider) | Yahoo Finance via yfinance.download; daily unadjusted Close in USD; provider rights and production approval are unverified. | bronze/ingest_prices.py; README.md
Reference | Instrument mapping | PARTIALLY IMPLEMENTED | Ten instrument_id-to-symbol mappings in Python configuration; books and counterparties are opaque input strings. | trade_pipeline/config.py
Governance | Unity Catalog | IMPLEMENTED | Catalog cibc with bronze, silver, and gold schemas and a bronze trade_files Volume. | database/catalog.sql; database schemas and Volume DDL
Bronze | Raw Delta tables | IMPLEMENTED | cibc.bronze.trades is a validated full snapshot overwrite; cibc.bronze.market_prices is merged by symbol and date. | database/tables/bronze/*.sql; bronze modules
Silver | Validation and rejects | IMPLEMENTED | Typed trade and price tables with business validation, version selection, lineage, and history-preserving reject tables. | silver modules; database/tables/silver/*.sql
Gold | Positions | IMPLEMENTED | Cumulative signed quantities by valuation date, book, counterparty, instrument, and currency; exact-date close valuation. | gold/build_positions.py; cibc.gold.positions
Gold | Daily P&L | IMPLEMENTED (simplified) | Opening inventory market move plus the signed trade-to-close term; missing current/baseline prices yield NULL and breaks. | gold/calculate_daily_pnl.py; cibc.gold.daily_pnl
Workflow | Databricks Job | IMPLEMENTED; dev only | Six wheel tasks; trade and price branches run in parallel, converge at build_positions, then calculate_daily_pnl. | jobs/resources/trade_pipeline.job.yml
Operations | Audit and exception data | PARTIALLY IMPLEMENTED | Task-attempt audit log, Silver reject history, and run-level valuation breaks; automated notifications are not evidenced. | trade_pipeline/audit.py; gold/break_report.py
Reporting | Current report surfaces | PARTIALLY IMPLEMENTED | Run-trigger and read-only report notebooks plus demo SQL; no deployed dashboard is evidenced. | notebooks/01_run_pipeline.py; notebooks/02_pipeline_report.py; docs/demo_queries.sql
Deployment | Asset Bundle | PARTIALLY IMPLEMENTED | Python wheel build and Databricks Asset Bundle dev target; schedule configured PAUSED; no CI or non-dev target is evidenced. | databricks.yml; jobs/resources/trade_pipeline.job.yml; scripts/deploy.sh
Target | Enterprise source contracts | PLANNED / NOT VERIFIED | Approved trade and licensed market-data contracts, rights, completeness SLAs, and correction semantics. | Open source decisions
Target | Security and operations | PLANNED / NOT VERIFIED | Provisioned runtime identity, least-privilege review, automated alerts, retention/recovery policy, and named support ownership. | Open readiness gates
Target | Dashboard | BLOCKED | User-accepted reporting dashboard and controlled access after audience and requirements are approved. | TMP-020; reporting/access decisions pending
Workflow Task | ingest_prices | IMPLEMENTED | Downloads daily unadjusted closes and merges raw price records to Bronze. | jobs/resources/trade_pipeline.job.yml; trade_pipeline/bronze/ingest_prices.py
Workflow Task | process_prices | IMPLEMENTED | Validates Bronze prices, checks expected sessions, merges typed Silver prices, and records rejects. | jobs/resources/trade_pipeline.job.yml; trade_pipeline/silver/process_prices.py
Workflow Task | ingest_trades | IMPLEMENTED | Validates the 14-column CSV structure and replaces the Bronze trade snapshot. | jobs/resources/trade_pipeline.job.yml; trade_pipeline/bronze/ingest_trades.py
Workflow Task | process_trades | IMPLEMENTED | Casts and validates trades, selects the latest usable version, and writes reject history. | jobs/resources/trade_pipeline.job.yml; trade_pipeline/silver/process_trades.py
Workflow Task | build_positions | IMPLEMENTED | Aggregates signed trades into daily cumulative positions and exact-date valuation. | jobs/resources/trade_pipeline.job.yml; trade_pipeline/gold/build_positions.py
Workflow Task | calculate_daily_pnl | IMPLEMENTED | Calculates simplified daily cash-equity P&L and missing-price/baseline breaks. | jobs/resources/trade_pipeline.job.yml; trade_pipeline/gold/calculate_daily_pnl.py

## Stakeholder Register
Stakeholder role | Responsibility | Engagement approach | Decision authority | Communication frequency | Assignment / evidence status
Project Sponsor | Own business outcome, funding/capacity decisions, escalation and scope trade-offs. | Steering summary, decision log and milestone gates. | Approve project scope changes and prototype exit/go-no-go. | Biweekly steering and milestone decisions (proposed). | Role required; named person not evidenced.
Technical Project Manager | Integrated plan, RAID, dependency management, governance, decisions, reporting and release readiness. | Daily coordination; weekly workstream and RAID review; steering pack. | Coordinate baseline and escalate; sponsor retains scope/budget authority. | Daily / weekly / milestone cadence. | Role assumed for interview plan; no actual allocation evidence.
Business Analyst / Product Owner | Business requirements, acceptance criteria, prioritization, UAT and reporting needs. | Workshops, backlog refinement, sprint reviews and sign-off. | Approve business requirements and acceptance within delegated scope. | Part-time weekly; each sprint review (proposed). | Part-time role assumed; name not evidenced.
Solution Architect | Architecture, integration contracts, data/security design and technical decisions. | Design reviews, dependency/risk review and change impact. | Recommend/approve design within architecture governance. | At design gates and material changes (proposed). | Part-time role assumed; name not evidenced.
Data Engineering | PySpark/SQL, Delta models, workflows, tests, CI/CD and technical runbooks. | Daily stand-up, PR reviews, demos and incident triage. | Technical implementation and evidence; not business P&L sign-off. | Daily; sprint cadence. | One lead engineer assumed; no named assignment evidenced.
Product Control | Challenge valuation/P&L methodology, reconciliation tolerances and business acceptance. | Calculation design review, exception review and UAT. | Approve business calculation interpretation within delegated control framework. | Design gate and weekly UAT window (proposed). | Required role; participant not evidenced.
Trading Operations | Trade source delivery, completeness, corrections/cancellations and day-to-day operating process. | Source-contract workshop, exception runbook and handover. | Confirm operational source semantics and cutoff; not provider licensing. | Weekly during source onboarding and handover (proposed). | Required role; participant not evidenced.
Information Security | Review identity, least privilege, secrets, data classification and deployment controls. | Architecture/security review and release readiness. | Approve security controls under applicable policy. | Design gate and before non-dev deployment (proposed). | Required reviewer; approval not evidenced.
QA | Test strategy, test evidence, defect triage, regression, reconciliation and UAT coordination. | Refinement, test reviews, sprint demos and release gate. | Report test status and quality risk; does not approve business methodology. | Part-time weekly; focused at test/release sprints. | Part-time support assumed; name not evidenced.
Production Support | Monitoring, incident response, rerun/recovery, runbook, service ownership and handover. | Operational design review, alert test and handover walkthrough. | Accept operational readiness within support mandate. | At design gate and before handover (proposed). | Required role; service owner not evidenced.
Market Data Owner | Provider selection, data rights, close definition, corrections, delivery SLA and completeness. | Source decision and exception review. | Approve market-data source and contractual/data-rights use. | At source selection and service review (proposed). | Role required; owner/provider approval not evidenced.

## RACI Matrix
Activity | Project Sponsor | Technical Project Manager | Business Analyst / Product Owner | Solution Architect | Data Engineering | Product Control | Trading Operations | Information Security | QA | Production Support
Scope, funding and priority decisions | A | R | C | C | I | C | C | I | I | I
Business/functional requirements and acceptance | I | C | A/R | C | C | C | C | I | C | I
Architecture and technical data design | I | C | C | A/R | R | C | C | C | C | C
Trade source contract and correction semantics | I | C | C | C | R | C | A | I | C | C
Market-data provider and rights decision | I | C | C | C | R | C | C | C | I | I
Security/access architecture review | I | C | I | R | C | I | I | A | I | C
Build, unit tests and CI/CD implementation | I | C | I | C | A/R | I | I | C | C | I
P&L methodology and reconciliation acceptance | I | C | R | C | R | A | C | I | R | I
Release readiness and operational handover | A | R | C | C | R | C | C | C | R | R

## Integrated Delivery Plan
Workstream ID | Activity | Proposed owner role | Duration (weeks) | Start week | End week | Predecessors | Milestone | Implementation status | Story IDs
WS-01 | Requirements and scope | Proposed role; see Stakeholders_RACI | 2 | 1 | 2 | None | M-01 | PARTIALLY IMPLEMENTED | TMP-001; TMP-002; TMP-003
WS-02 | Trade source contract | Proposed role; see Stakeholders_RACI | 2 | 1 | 2 | None | M-01 | PARTIALLY IMPLEMENTED | TMP-006
WS-03 | Security and environment design | Proposed role; see Stakeholders_RACI | 2 | 3 | 4 | WS-01; TMP-004 | M-02 | PLANNED | TMP-005
WS-04 | Market-data provider decision | Proposed role; see Stakeholders_RACI | 2 | 3 | 4 | WS-01 | M-02 | PLANNED | TMP-007
WS-05 | Workflow and schedule gate | Proposed role; see Stakeholders_RACI | 2 | 3 | 4 | TMP-009 | M-02 | PARTIALLY IMPLEMENTED | TMP-023
WS-06 | CI/CD promotion controls | Proposed role; see Stakeholders_RACI | 2 | 5 | 6 | WS-03; TMP-009 | M-03 | PLANNED | TMP-010
WS-07 | Trade correction and history | Proposed role; see Stakeholders_RACI | 2 | 5 | 6 | WS-02; TMP-011 | M-03 | PLANNED | TMP-012
WS-08 | Spark/Delta rerun validation | Proposed role; see Stakeholders_RACI | 2 | 7 | 8 | TMP-015 | M-04 | PLANNED | TMP-016
WS-09 | Test maintenance and QA | Proposed role; see Stakeholders_RACI | 2 | 7 | 8 | None | M-04 | PARTIALLY IMPLEMENTED | TMP-021
WS-10 | Reconciliation and UAT | Proposed role; see Stakeholders_RACI | 2 | 7 | 8 | WS-08; TMP-018 | M-04 | PARTIALLY IMPLEMENTED | TMP-022
WS-11 | Operations handover | Proposed role; see Stakeholders_RACI | 2 | 7 | 8 | WS-01; WS-05; WS-10; TMP-019 | M-04 | PLANNED | TMP-024

## Resource Capacity
Delivery role | Capacity assumption | Workstream allocation | Estimated effort (person-days) | Estimate basis | Capacity constraints / status
Technical Project Manager | 0.4 FTE; 4 person-days per 2-week sprint | Integrated plan, dependencies, RAID, decisions, reporting and readiness | 16 | Baseline effort = capacity per sprint × 4 sprints | Proposed capacity; no named assignment or competing demand verified.
Lead Data Engineer | 1.0 FTE; 10 person-days per sprint | PySpark/SQL, Delta, tests, Bundle/CI and technical runbooks | 40 | Baseline effort = capacity per sprint × 4 sprints | Single-engineer bottleneck; 10 SP/sprint planning cap is an assumption, not measured velocity.
Business Analyst / Product Owner | 0.3 FTE; 3 person-days per sprint | Requirements, acceptance criteria, prioritization, UAT | 12 | Baseline effort = capacity per sprint × 4 sprints | Part-time decision availability; response latency can block approval gates.
Solution Architect | 0.2 FTE; 2 person-days per sprint | Architecture, source integration, data and security design reviews | 8 | Baseline effort = capacity per sprint × 4 sprints | Part-time; review windows must be booked around design gates.
QA | 0.3 FTE; 3 person-days per sprint | Test planning, supported-runtime tests, defect triage, UAT support | 12 | Baseline effort = capacity per sprint × 4 sprints | Spark/Delta environment access is a prerequisite; availability unconfirmed.
Product Control | 0.1 FTE; 1 person-day per sprint | Calculation methodology, materiality, reconciliation and acceptance | 4 | Baseline effort = capacity per sprint × 4 sprints | Business calculation owner and tolerance are not identified.
Trading Operations | 0.1 FTE; 1 person-day per sprint | Source contract, completeness/correction rules and operating process | 4 | Baseline effort = capacity per sprint × 4 sprints | Source owner/cutoff not evidenced; availability is proposed.
Information Security | 0.1 FTE; 1 person-day per sprint | Access, identity, data classification and release review | 4 | Baseline effort = capacity per sprint × 4 sprints | Security reviewer and applicable controls must be confirmed.
Production Support | 0.1 FTE; 1 person-day per sprint | Monitoring, rerun/recovery process, operational acceptance and handover | 4 | Baseline effort = capacity per sprint × 4 sprints | Support owner, hours, SLA and escalation channel not evidenced.

## Governance
Activity | Purpose | Participants | Frequency | Outputs | Escalation route
Engineering stand-up | Surface progress, next steps, blockers and cross-branch dependencies; keep it to delivery decisions. | TPM, Data Engineering, BA/PO, QA as needed | Daily, 15 minutes (proposed). | Updated actions, blockers and dependency owner/date. | Blocker unresolved by next working day → TPM; scope/date/decision blockage → Sponsor or accountable owner.
Workstream review | Review trade, price, platform, calculation, test and reporting work against sprint outcomes. | TPM, workstream leads, BA/PO, Architect, QA and invited control/operations owners | Weekly (proposed). | Forecast, dependency changes, decisions, acceptance evidence. | Cross-workstream conflict → TPM; architecture/security decision → review owner; scope trade-off → Sponsor.
RAID and change review | Reassess probability/impact, triggers, owners, due dates and change requests. | TPM, story owners, BA/PO, Architect, QA; Sponsor for high impact | Weekly and at material change (proposed). | RAID actions, change-impact assessment, decision-log updates. | High-impact / near-term trigger → Sponsor and affected control owner immediately; unresolved policy risk blocks release.
Architecture and security review | Review provider interface, data contracts, UC permissions, identity, secrets and deployment boundary. | Solution Architect, Information Security, Data Engineering, Platform owner, Production Support | At design baseline and before material change or non-dev deployment. | Decision record, approved design constraints, security actions. | Unapproved data rights/access or policy exception → accountable Security/Architecture authority; no production promotion.
Steering update | Give concise evidence-based status and obtain scope/capacity decisions. | Sponsor, TPM, BA/PO, Architect, engineering and relevant business/control owners | Biweekly or at milestone gates (proposed). | RAG status, milestone forecast, top RAID, decisions, change approvals. | Sponsor decision; record outcome and effect on scope, capacity, schedule and risk.
Milestone approval gate | Confirm specific acceptance evidence before entering dependent work or presenting readiness. | Named accountable milestone owner and required approvers listed in Milestone Tracker. | End of Weeks 2, 4, 6, 8; optional Week 10 follow-on. | Approve / reject / conditional approval, evidence links, actions and owner/date. | Missing approval or failed criterion → hold dependent work/release and escalate to Sponsor; do not infer approval from demo.
Release readiness review | Assess source, security, quality, monitoring, recovery, support and business acceptance before any schedule activation. | Sponsor, Product Control, QA, Security, Production Support, TPM, Architect and Data Engineering | Once before any non-dev release or schedule unpause; repeat after material scope change. | Readiness checklist, explicit go/no-go, residual risk acceptance and rollback plan. | Any critical control/source/UAT/support gap → no-go; Sponsor cannot waive policy-owner approval.

## Change Control
Change request | Request / status | Business justification | Scope impact | Schedule impact | Resource impact | Risk impact | Decision | Approver | Status
CR-LOG | No actual change request evidenced as of 2026-10-14 | No submitted/approved change is recorded in the repository evidence. | No approved change to current USD cash-equity prototype scope. | No actual schedule impact recorded. | No approved resource impact recorded. | Any new request is assessed through change control; multi-currency example is hypothetical only. | No change decision recorded; use this register for new requests. | Not applicable; approver roles are defined in governance/RACI. | NOT VERIFIED

## TPM Scenarios
Scenario ID | Label | Trigger | Delivery impact | Critical dependencies | Mitigation | Escalation | Contingency | Decision required | Status
SC-A | HYPOTHETICAL: market-data provider approval is delayed | Provider rights or source-owner approval is not available by the Sprint 2 source gate. | Production data path and price SLA remain unapproved; integration/UAT evidence is limited to existing prototype provider and deterministic fixtures; downstream valuation sign-off is at risk. | Market Data Owner decision; contract/data-rights review; interface and price definition; fixture availability. | Continue provider-neutral contract tests and synthetic fixture work; isolate adapter; keep Yahoo Finance prototype-only; do not claim a production feed. | TPM raises at weekly RAID and immediately to Sponsor/Market Data Owner if the Week 4 gate is threatened; Security/Legal/Data Governance consulted as required. | Defer production source integration and dashboard UAT; use optional Sprint 5 or rebaseline after decision; do not bypass licensing. | Sponsor accepts scope/date trade-off; authorized Market Data Owner approves provider, rights, and service expectations. | Hypothetical only; not an actual incident.
SC-B | HYPOTHETICAL: multi-currency P&L requested during implementation | Business requests non-USD P&L after the USD prototype scope is baselined. | Adds FX source/rates, currency/date conventions, conversion policy, model dimensions, decimal/rounding rules, valuation/P&L logic, tests, dashboard filters, and control sign-off; 8-week baseline is not assumed to absorb it. | Currency and FX business rules; approved FX provider; accounting/Product Control policy; reference mapping and data model review. | Log a change request; BA/Architect/Data Engineering/QA/Product Control estimate impact and identify affected BR/FR, tables, stories and tests; keep USD-only baseline unchanged pending approval. | TPM presents options and impact at steering; Sponsor owns scope/capacity trade-off; Product Control and architecture/security owners approve their domains. | Defer multi-currency to separately estimated release or swap explicitly lower-priority dashboard scope; add capacity/sprint only after resource confirmation. | Approve, reject, or defer by named Sponsor with documented Product Control methodology approval; update baseline and traceability before work starts. | Hypothetical only; no such request is evidenced.
SC-C | HYPOTHETICAL: position or P&L reconciliation identifies incorrect results | Independent SQL/UAT reconciliation finds a material quantity, valuation, or P&L mismatch. | Affected output is not accepted; any dependent dashboard/demo/release is held; assess impacted dates/books/instruments and downstream users before reuse. | Reproducible input snapshot/run ID; expected calculation; defect severity/materiality; Product Control decision. | Stop promotion; preserve run and input evidence; compare Bronze→Silver→Gold by business key; classify source, transform, calendar, price, or methodology defect; create defect and regression test; rerun and reconcile corrected scope. | QA alerts TPM and Product Control immediately for material financial mismatch; TPM escalates release impact to Sponsor and Production Support; security/data incident path if exposure or integrity breach is suspected. | Rollback/retain last accepted dataset where supported; mark output unavailable rather than zero or silently corrected; replan dependent milestones after root cause and fix. | Product Control accepts calculation result/tolerance; QA confirms regression; release authority records go/no-go and residual risk. | Hypothetical only; not an actual incident.